## SHEET
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of March 31, 2019
PROGRAM OR PROJECT |  |  |  | LOCATION |  | DATE STARTED |  | OBLIGATION
[5 empty] | TOTAL COST |  | TARGET | % OF | TOTAL | REMARKS
[5 empty] | Appropriation |  | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[7 empty] | DATE | APPROPRIATION | TO DATE
Annual Budget
SOCIAL DEVELOPMENT:
1918 (C.O)
Construction of Gym, Purok 2, Poblacion, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Construction of Gym, Mangayon NHS, Brgy. Mangayon, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Concreting of Road going to Valderama ES & NHS, Brgy. Ngan, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | Purchase Request on Process
Improvement of Water System, Brgy. Babag, Monkayo |  |  |  | Monkayo | 1200000 |  |  | 0% | 0 | Program of Works for Approval
Construction of Brgy. Stage, Brgy. Kao, Nabunturan |  |  |  | Nabunturan | 850000 |  |  | 0% | 0 | Purchase Request on Process
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  |  | New Bataan | 3000000 |  |  | 0% | 0 | For change in nomenclature from renovation to construction
Rehabilitation of Level II Water System, Brgy. Belmonte, Laak |  |  |  | Laak | 1500000 |  |  | 0% | 0 | For Detailed Engineering Design
Construction of Gym, Brgy. Poblacion, Maco |  |  |  | Maco | 5000000 |  |  | 0% | 0 | CONTRACT. Purchase Request on Process
Construction of Water System, Brgy. Taglawig, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0 | Program of Works on process.
Construction of Gym, Sitio Boringot, Brgy. Napnapan, Pantukan |  |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym, Sitio Panganason, Brgy, Kingking, Pantukan |  |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym Brgy. Tagdangua, Pantukan |  |  |  | Pantukan | 4000000 |  |  | 0% | 0 | For verification of project location. Waiting for brgy. captain's recommendation
Completion of Multi-purpose Building, Brgy Kingking, Pantukan NHS |  |  |  | Pantukan | 2000000 |  |  | 0% | 0 | Purchase Request on Process
Completion of Multi-purpose Building, Brgy. Kingking CES. Pantukan |  |  |  | Pantukan | 1000000 |  |  | 0% | 0 | Purchase Request on Process
Renovation of Dry Market, Brgy. Poblacion, Monkayo |  |  |  | Monkayo | 3000000 |  |  | 0% | 0
Construction of Brgy. Del Pilar Gym, Brgy. Del Pilar, Mabini |  |  |  | Mabini | 3000000 |  |  | 0% | 0
Development of Eco- Tourism Park Phase 2, Pantukan |  |  |  | Pantukan | 5000000 |  |  | 0%
Construction of Brgy. Stage, Brgy. Nuevo Iloco, Mawab |  |  |  | Mawab | 850000 |  |  | 0% | 0
Purchase of Lot for Happy Village, Brgy. Nueva Visayas, Mawab |  |  |  | Mawab | 2000000 |  |  | 0% | 0
Purchase of lot for the Expansion of Compostela Valley Provincial Hospitals |  |  |  |  | 3000000 |  |  | 0% | 0
Purchase of lot for the Development of Provincial Sports Complex |  |  |  |  | 12000000 |  |  | 0% | 0
Sub - Total Social Development |  |  |  |  | 66400000 |  |  |  | 0
ECONOMIC DEVELOPMENT:
1918 (MOOE)
Provincial Counterpart for Special Projects |  |  |  |  | 26719272.38 |  |  | 0% | 0
8917 (CO)
Rehabilitation Of Provincial Roads/ Bridges - District 1 |  |  |  | Provincewide | 28917741 |  |  | 4.801% | 1388279.87 | 4.80% Accomplished
Rehabilitation Of Provincial Roads/ Bridges - District 2 |  |  |  | Provincewide | 28584329 |  |  | 10.49% | 2999297.21 | 10.49% Accomplished
Rehabilitation of Farm-to-Market Roads (FMRS) - Provincewide |  |  |  | Provincewide | 5000000 |  |  | 0% | 0
Sub - Total Economic Development |  |  |  |  | 89221342.38 |  |  |  | 4387577.08
OTHER SERVICES:
1918 (CO)
Construction of Multi-Purpose Building - Provincewide |  |  |  | Provincewide | 1800000 |  |  | 0% | 0
Rehabilitation of Water System |  |  |  |  | 5000000 |  |  | 0% | 0
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  |  | 18109696.62 |  |  | 67.8% | 12279081.78 | Paid to Land Bank
| Loans Payable |  |  |  | 114338961 |  |  | 42.51% | 48605518.53 | Paid to Land Bank
Sub - Total Other Purposes |  |  |  |  | 139248657.62 |  |  |  | 60884600.31
Total Annual Budget |  |  |  |  | 294870000 |  |  |  | 65272177.39
Supplemental Budget No. 1
1918 (C.O)
Completion of Covered Court - Kinuban, Maco |  |  |  | Maco | 66304.34 |  |  | 0% | 0
Const. of PDEA MP Bldg., PPO-Nabunturan |  |  |  | Nabunturan | 62666.01 |  |  | 0% | 0
Imp. of MP Building- Maragusan |  |  |  | Maragusan | 5000000 |  |  | 0% | 0
Const. of Covered Court - Tagugpo NHS |  |  |  | Pantukan | 1150000 |  |  | 0% | 0
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  |  | New Bataan | 2000000 |  |  | 0% | 0
Completion of Municipal Tribal Hall, Pantukan |  |  |  | Pantukan | 2500000 |  |  | 0% | 0
Imp. of MP Bulding (Women Crisis Center), Brgy. Cabidianan, Nabunturan |  |  |  | Nabunturan | 3000000 |  |  | 0% | 0
Const. of MP Building (Bahay Pag-Asa) |  |  |  |  | 1000000 |  |  | 0% | 0
Const. of Gym, Brgy. Teresa, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0
Const. of PDEA MP Bldg., PPO-Nabunturan- Phase II |  |  |  | Nabunturan | 2500000 |  |  | 0% | 0
Const. of Covered Court - Kidawa, Laak |  |  |  | Laak | 220000 |  |  | 0% | 0
Conc. of Road with Drainage Component, Brgy. Cabidianan, Nabunturan |  |  |  | Nabunturan | 2833114.38 |  |  | 0% | 0
Conc. of Junction Nat'l Highway - Purok 2 to PRC, Brgy. Sta. Maria |  |  |  | Nabunturan | 1486992.37 |  |  | 0% | 0
Const. of Brgy. Stage, Brgy. Nueva Visayas, Mawab |  |  |  | Mawab | 850000 |  |  | 0% | 0
Imp. of Water System-Coronobe, Maragusan |  |  |  | Maragusan | 489400 |  |  | 0% | 0
Const. of WS, Brgy. Del Pilar, Mabini |  |  |  | Mabini | 3000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Tagnocon, Nabunturan |  |  |  | Nabunturan | 3000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Kinuban, Maco |  |  |  | Maco | 5000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Panibasan, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0
Imp. of WS-Brgy. Babag, Monkayo |  |  |  | Monkayo | 427500 |  |  | 0% | 0
Const. of Health Center-Mapaang, Maco |  |  |  | Maco | 1500000 |  |  | 0% | 0
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  |  | 3557622.9 |  |  | 0% | 0
Total Supplemental Budget No. 1 |  |  |  |  | 45643600 |  |  |  | 0
Grand Total |  |  |  |  | 340513600 |  |  |  | 65272177.39
Summary: | [7 empty] | %of Obligation/
[5 empty] | Appropriation |  |  | Appropriation | Obligation
| 1918 | Social Development |  |  | 115285977.1 |  |  | 0% | 0
| 8917 | Economic Development |  |  | 89221342.38 |  |  | 4.918% | 4387577.08
| 9911 | Financial Expenses |  |  | 136006280.52 |  |  | 44.77% | 60884600.31
|  | Grand Total |  |  | 340513600 |  |  | 19.17% | 65272177.39
|  |  |  | check | 340513600
0
65272177.39
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  | As to Appropriation/Obligation |  |  | As to Project Status: |  |  |  | Approved:
|  | EVA JEAN S. LICAYAN, ENP, REB, MPA |  | ROMEO B. CELESTE, ENP |  | ENGR. RODERICK M. DIGAMON |  |  | JAYVEE TRON L. UY, MPA
|  | Provincial Budget Officer |  | Provincial Planning & Development Office |  | Provincial Engineer's Office |  |  | Governor
282039226.9
-58474373.1

## PRINT
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of March 31, 2019
PROGRAM OR PROJECT |  |  | LOCATION |  | DATE STARTED |  | OBLIGATION
|  |  |  | TOTAL COST |  | TARGET | % OF | TOTAL | REMARKS
|  |  |  | Appropriation |  | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[6 empty] | DATE | APPROPRIATION | TO DATE
Annual Budget
SOCIAL DEVELOPMENT:
1918 (C.O)
Construction of Gym, Purok 2, Poblacion, Compostela |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Construction of Gym, Mangayon NHS, Brgy. Mangayon, Compostela |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Concreting of Road going to Valderama ES & NHS, Brgy. Ngan, Compostela |  |  | Compostela | 3000000 |  |  | 0% | 0 | Purchase Request on Process
Improvement of Water System, Brgy. Babag, Monkayo |  |  | Monkayo | 1200000 |  |  | 0% | 0 | Program of Works for Approval
Construction of Brgy. Stage, Brgy. Kao, Nabunturan |  |  | Nabunturan | 850000 |  |  | 0% | 0 | Purchase Request on Process
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  | New Bataan | 3000000 |  |  | 0% | 0 | For change in nomenclature from renovation to construction
Rehabilitation of Level II Water System, Brgy. Belmonte, Laak |  |  | Laak | 1500000 |  |  | 0% | 0 | For Detailed Engineering Design
Construction of Gym, Brgy. Poblacion, Maco |  |  | Maco | 5000000 |  |  | 0% | 0 | CONTRACT. Purchase Request on Process
Construction of Water System, Brgy. Taglawig, Maco |  |  | Maco | 3000000 |  |  | 0% | 0 | Program of Works on process.
Construction of Gym, Sitio Boringot, Brgy. Napnapan, Pantukan |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym, Sitio Panganason, Brgy, Kingking, Pantukan |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym Brgy. Tagdangua, Pantukan |  |  | Pantukan | 4000000 |  |  | 0% | 0 | For verification of project location. Waiting for brgy. captain's recommendation
Completion of Multi-purpose Building, Brgy Kingking, Pantukan NHS |  |  | Pantukan | 2000000 |  |  | 0% | 0 | Purchase Request on Process
Completion of Multi-purpose Building, Brgy. Kingking CES. Pantukan |  |  | Pantukan | 1000000 |  |  | 0% | 0 | Purchase Request on Process
Renovation of Dry Market, Brgy. Poblacion, Monkayo |  |  | Monkayo | 3000000 |  |  | 0% | 0 | for Fund Transfer to Municipality (FTM)
Construction of Brgy. Del Pilar Gym, Brgy. Del Pilar, Mabini |  |  | Mabini | 3000000 |  |  | 0% | 0 | Declared abandoned & savings per SP Res. No. 1296-2019
Development of Eco- Tourism Park Phase 2, Pantukan |  |  | Pantukan | 5000000 |  |  | 0% | 0 | for Fund Transfer to Municipality (FTM)
Construction of Brgy. Stage, Brgy. Nuevo Iloco, Mawab |  |  | Mawab | 850000 |  |  | 0% | 0 | Declared abandoned & savings per SP Res. No. 1296-2019
Purchase of Lot for Happy Village, Brgy. Nueva Visayas, Mawab |  |  | Mawab | 2000000 |  |  | 0% | 0 | For Implementation
Purchase of lot for the Expansion of Compostela Valley Provincial Hospitals |  |  |  | 3000000 |  |  | 0% | 0 | For Implementation
Purchase of lot for the Development of Provincial Sports Complex |  |  |  | 12000000 |  |  | 0% | 0 | For Implementation
Sub - Total Social Development |  |  |  | 66400000 |  |  |  | 0
ECONOMIC DEVELOPMENT:
1918 (MOOE)
Provincial Counterpart for Special Projects |  |  |  | 26719272.38 |  |  | 0% | 0 | For Implementation
8917 (CO)
Rehabilitation Of Provincial Roads/ Bridges - District 1 |  |  | Provincewide | 28917741 |  |  | 4.801% | 1388279.87 | On-Going
Rehabilitation Of Provincial Roads/ Bridges - District 2 |  |  | Provincewide | 28584329 |  |  | 10.49% | 2999297.21 | On-Going
Rehabilitation of Farm-to-Market Roads (FMRS) - Provincewide |  |  | Provincewide | 5000000 |  |  | 0% | 0 | For Implementation
Sub - Total Economic Development |  |  |  | 89221342.38 |  |  |  | 4387577.08
OTHER SERVICES:
1918 (CO)
Construction of Multi-Purpose Building - Provincewide |  |  | Provincewide | 1800000 |  |  | 0% | 0 | For Implementation
Rehabilitation of Water System |  |  |  | 5000000 |  |  | 0% | 0 | For Implementation
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  | 18109696.62 |  |  | 67.8% | 12279081.78 | Paid to Land Bank
| Loans Payable |  |  | 114338961 |  |  | 42.51% | 48605518.53 | Paid to Land Bank
Sub - Total Other Purposes |  |  |  | 139248657.62 |  |  |  | 60884600.31
Total Annual Budget |  |  |  | 294870000 |  |  |  | 65272177.39
Supplemental Budget No. 1
1918 (C.O)
Completion of Covered Court - Kinuban, Maco |  |  | Maco | 66304.34 |  |  | 0% | 0 | Project Completed. Date of Completion - February 09, 2019 (Contractor- LLM Unified and Trading Corp.)
Const. of PDEA MP Bldg., PPO-Nabunturan |  |  | Nabunturan | 62666.01 |  |  | 0% | 0 | POW on process
Imp. of MP Building- Maragusan |  |  | Maragusan | 5000000 |  |  | 0% | 0
Const. of Covered Court - Tagugpo NHS |  |  | Pantukan | 1150000 |  |  | 0% | 0 | POW for approval
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  | New Bataan | 2000000 |  |  | 0% | 0 | POW on process
Completion of Municipal Tribal Hall, Pantukan |  |  | Pantukan | 2500000 |  |  | 0% | 0 | POW for approval
Imp. of MP Bulding (Women Crisis Center), Brgy. Cabidianan, Nabunturan |  |  | Nabunturan | 3000000 |  |  | 0% | 0 | Waiting for reference from the national office
Const. of MP Building (Bahay Pag-Asa) |  |  |  | 1000000 |  |  | 0% | 0 | Plans and Drawings on Process
Const. of Gym, Brgy. Teresa, Maco |  |  | Maco | 3000000 |  |  | 0% | 0 | POW on process
Const. of PDEA MP Bldg., PPO-Nabunturan- Phase II |  |  | Nabunturan | 2500000 |  |  | 0% | 0 | Plans and Drawings on Process
Const. of Covered Court - Kidawa, Laak |  |  | Laak | 220000 |  |  | 0% | 0 | Waiting for SPP
Conc. of Road with Drainage Component, Brgy. Cabidianan, Nabunturan |  |  | Nabunturan | 2833114.38 |  |  | 0% | 0 | Waiting for the settlement of Road Right of Way
Conc. of Junction Nat'l Highway - Purok 2 to PRC, Brgy. Sta. Maria |  |  | Nabunturan | 1486992.37 |  |  | 0% | 0 | Waiting for the settlement of Road Right of Way
Const. of Brgy. Stage, Brgy. Nueva Visayas, Mawab |  |  | Mawab | 850000 |  |  | 0% | 0 | POW on process
Imp. of Water System-Coronobe, Maragusan |  |  | Maragusan | 489400 |  |  | 0% | 0 | For inspection
Const. of WS, Brgy. Del Pilar, Mabini |  |  | Mabini | 3000000 |  |  | 0% | 0 | For survey
Const. of Potable WS, Brgy. Tagnocon, Nabunturan |  |  | Nabunturan | 3000000 |  |  | 0% | 0 | Detailed Engineering Design on process
Const. of Potable WS, Brgy. Kinuban, Maco |  |  | Maco | 5000000 |  |  | 0% | 0 | For survey
Const. of Potable WS, Brgy. Panibasan, Maco |  |  | Maco | 3000000 |  |  | 0% | 0 | For survey
Imp. of WS-Brgy. Babag, Monkayo |  |  | Monkayo | 427500 |  |  | 0% | 0 | POW for approval
Const. of Health Center-Mapaang, Maco |  |  | Maco | 1500000 |  |  | 0% | 0 | POW on process
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  | 3557622.9 |  |  | 0% | 0
Total Supplemental Budget No. 1 |  |  |  | 45643600 |  |  |  | 0
Grand Total |  |  |  | 340513600 |  |  |  | 65272177.39
Summary: | [6 empty] | %of Obligation/
|  |  |  | Appropriation |  |  | Appropriation | Obligation
| 1918 | Other Services |  | 6800000 |  |  | 0% | 0
| 1918 | Social Development |  | 108485977.1 |  |  | 0% | 0
| 8917 | Economic Development |  | 89221342.38 |  |  | 4.918% | 4387577.08
| 9911 | Financial Expenses |  | 136006280.52 |  |  | 44.77% | 60884600.31
|  | Grand Total |  | 340513600 |  |  | 19.17% | 65272177.39
[10 empty] | 340513600 | 65272177.39
[10 empty] | 0 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| As to Appropriation/Obligation |  | As to Project Status: |  |  |  |  | Approved:
| EVA JEAN S. LICAYAN, ENP, REB, MPA |  | ROMEO B. CELESTE, ENP |  | ENGR. RODERICK M. DIGAMON |  |  | JAYVEE TRON L. UY, MPA
| Provincial Budget Officer |  | Provincial Planning & Development Office |  | Provincial Engineer's Office |  |  | Governor
282039226.9
-58474373.1

## roads and bridges
d1 |  | d2
1406312.94 | 1 | 450666.82
346641.07 | 2 | 3691173.19
329338.25 | 3 | 1187823.25
860736.66 | 4 | 302357.89
754121.02 | 5 | 443858.29
665957.25 | 6 | 374428.06
544873.39 | 7 | 639808.52
1353782.24 | 8 | 1222449.7
1587558.73 | 9 | 961270.42
1551379.51 | 10 | 502575.03
1069370.6 | 11 | 358411.19
607875.22 | 12 | 375094.6
721191.34 | 13 | 146437.95
963298.57 | 14 | 236740.16
2760936.08 | 15 | 291795.83
1286500.07 | 16 | 1874149.59
870815.18 | 17 | 596713.11
418001.17 | 18 | 375020.62
1505817.84 | 19 | 394342.91
1238228.44 | 20 | 601211.95
359101.69 | 21 | 370613.91
256470.21 | 22 | 450447.22
1002796.15 | 23 | 33831.18
738974.46 | 24 | 560682.9
1238663.92 | 25 | 287876.96
245287.26 | 26 | 190649.67
287922.45 | 27 | 374932.65
649684.57 | 28 | 300551.75
576306.14 | 29 | 252591.74
454766.29 | 30 | 245486.18
291166.54 | 31 | 174550.8
656730.56 | 32 | 495228.2
262775.76 | 33 | 117163.28
| 34 | 299344.62
27863381.57 | 35 | 374976.44
| 36 | 104511.58
| 37 | 375108.65
| 38 | 1493740.5
| 39 | 97714.15
| 40 | 296397.92
| 41 | 1109651.47
| 42 | 370132.58
| 43 | 600755.37
| 44 | 798288.05
| 45 | 1130549.9
| 46 | 427997.11
| 47 | 900692.95
| 48 | 749249.09
28010045.9

## July-Sept.
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST | DATE STARTED |  | OBLIGATION
[8 empty] | TARGET | % OF | TOTAL | REMARKS
[8 empty] | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[8 empty] | DATE | APPROPRIATION | TO DATE
1918 (MOOE)
SOCIAL DEVELOPMENT:
F/A Repair/Rehabilitation of Farm-to-Market Roads (FMR) |  |  |  |  | Provincewide | 5000000 |  |  | 0% |  | Program of works on process
F/A Provincial Counterpart for Special Programs/Projects |  |  |  |  | Provincewide | 10000000 |  |  | 0% |  | Program of works on process
F/A Repair/Rehabilitation of Water System |  |  |  |  | Provincewide | 4000000 |  |  | 0% |  | Program of works on process
Purchase of Various Sizes of HDPE Pipes
Distribution of Materials for Brgys. Magnaga, Bongbong, Matiao, Tambongon of Pantukan and Brgy. Pangi of Maco
F/A Construction/Purchase of Post Harvest Facilities |  |  |  |  | Provincewide | 1000000 |  |  | 0% |  | Procurement on process
F/A Completion of Multi-Purpose Building-Barangay Lahi, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Concreting of Barangay Road-Barangay Magcagong, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Acquisition of Dump Truck-Barangay New Manay, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Purok Multi-Purpose Center |  |  |  |  | Brgy. New Panay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Water System |  |  |  |  | Brgy. Talian, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. Mapawa, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. New Albay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Covered Court |  |  |  |  | Brgy. Mauswagon, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Multi-Purpose Building |  |  |  |  | Brgy. Coronobe, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Covered Court |  |  |  |  | Prk 1 Brgy. Paloc, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Purchase of Dump Truck |  |  |  |  | Laak | 2400000 |  |  | 0% |  | Procurement on process
F/A Construction of Covered Court |  |  |  |  | Brgy. Ceboleda, Laak | 1000000 |  |  | 76.27% | 762650.5 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Banbanon, Laak | 1000000 |  |  | 72.93% | 729340.48 | 20% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Bagong Silang, Laak | 1500000 |  |  | 71.54% | 1073131.28 | 15% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. New Bethlehem, Laak | 1000000 |  |  | 69.58% | 695782.73 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Kiokmay, Laak | 1000000 |  |  | 65.71% | 657073.29 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Cabuyuan, Mabini | 1000000 |  |  | 72.51% | 725068.58 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Salvacion, Mawab | 1000000 | 2017-06-27 | 2017-09-25 | 94.32% | 943242.52 | 30% 0n-going
Construction of Day Care Center- Sitio Cambodlot, San Miguel, Compostela |  |  |  |  | Compostela | 245446.21 | 2017-05-30 | 2017-08-18 | 90.62% | 222432.28 | 98% Temporarily Suspended.
Concreting of Road @ Bonifacio-Garcia St. Brgy. Poblacion, Compostela |  |  |  |  | Brgy. Compostela | 237240.2 | 2017-04-10 | 2017-05-05 | 95.16% | 225760.96 | Completed
Concreting of Road @ Emilio Aguinaldo St. Purok 1 |  |  |  |  | Brgy. Poblacion, Compostela | 206207.36 | 2017-05-02 | 2017-06-21 | 98.04% | 202175.97 | Completed
Concreting of Road from Brgy. Dauman to Brgy. Concepcion, Montevista |  |  |  |  | Brgy. Concepcion, Montevista | 1064369.3 | 2017-04-17 | 2017-08-25 | 96.26% | 1024555 | Completed
Concreting of Road Brgy. San Vicente, Montevista |  |  |  |  | Brgy. San Vicente, Montevista | 223652.46 | 2017-04-20 | 2017-06-20 | 97.43% | 217906.77 | Completed
Construction of Covered Court-Brgy. Cabacungan, Nabunturan |  |  |  |  | Brgy. Cabacungan, Nabunturan | 322320.39 | 2017-04-12 | 2017-07-27 | 57.83% | 186400.24 | Completed
Construction of Covered Court-Brgy. Basak (stage), Nabunturan |  |  |  |  | Nabunturan | 92762.56 | 2017-04-11 | 2017-05-24 | 99.2% | 92016.32 | Completed
F/A-Construction of Covered Court-Brgy. Mt. Diwata, Monkayo |  |  |  |  | Monkayo | 1000000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
Concreting of FMR, Purok 5, Tagaytay, Brgy. Mipangi, Nabunturan |  |  |  |  | Nabunturan | 267931.28 | 2017-05-02 | 2017-05-17 | 99.98% | 267886.12 | Completed
Concreting of Road from Junction National Highway to Purok 6 |  |  |  |  | Nabunturan | 1222342.98 | 2017-04-17 | 2017-08-15 | 55.44% | 677619.83 | 95% On-going
Concreting of Road at Brgy. Cabacungan, Nabunturan |  |  |  |  | Nabunturan | 576798.44 | 2017-04-12 | 2017-06-22 | 73.13% | 421799 | Completed
Concreting of Road from Junction Nat'l. H-way to Cabidianan Annex HS |  |  |  |  | Brgy. Nabunturan | 329035.58 | 2017-04-17 | 2017-07-05 | 95.32% | 313648.82 | Completed
Concreting of Road at Mapaang Section |  |  |  |  | Brgy. Mapaang, Maco | 212862.75 | 2017-05-16 | 2017-05-25 | 40.08% | 85316.88 | Completed
Construction of Multi-Purpose Building |  |  |  |  | Brgy. Poblacion, Mawab | 81822.86 | 2017-05-03 | 2017-06-07 | 71.44% | 58454.82 | 98% Temporarily Suspended.
Construction of Multi-Purpose Building (Council of Women) |  |  |  |  | Brgy. Las Arenas, Pantukan | 200030.48 | 2017-04-17 | 2017-06-20 | 63.25% | 126526.2 | 85% On-going
Construction of Tribal Hall |  |  |  |  | Brgy. Poblacion, Pantukan | 546787 | 2017-06-13 | 2017-10-06 | 35.96% | 196650.73 | 20% On-going
Construction of Multi-Purpose Building (Madrasah) |  |  |  |  | Tunga, Monkayo | 226099.1 | 2017-05-08 | 2017-07-18 | 55.51% | 125496.38 | 95% On-going
Construction of Multi-Purpose Building (ABC) |  |  |  |  | Compostela | 137322.6 | 2017-04-17 | 2017-06-15 | 98.16% | 134802.5 | Completed
Concreting of Road from Junction National H-way to Brgy. Hall |  |  |  |  | Bankerohan Sur, Montevista | 77881.34 | 2017-05-29 | 2017-06-13 | 94.37% | 73496.66 | Completed
Concreting of Road from Prk 8-Prk 7 to Junction National |  |  |  |  | Montevista | 420064.72 | 2017-04-17 | 2017-07-31 | 97.26% | 408538.38 | Completed
F/A Construction of Hanging Bridge (footbridge) Prk 9 |  |  |  |  | Salvacion, Monkayo | 650000 |  |  | 100% | 650000 | For Fund Transfer to Municipality (FTM)
F/A Construction of Slaughter House, Pantukan |  |  |  |  | Pantukan | 4700000 |  |  | 95.74% | 4500000 | For Fund Transfer to Municipality (FTM)
1918 (C.O)
Rehab. Of Brgy. Poblacion-Brgy. Naboc FMR, Monkayo (PRDP-BUILD) |  |  |  |  | Monkayo | 1358700 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Monkayo | 565505 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Maparat, Compostela | 521906 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Libasan, Nabunturan | 521902 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Linda, Nabunturan | 542264 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Kilagding, Laak | 543034 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Elizalde, Maco (OPPAP-PAMANA) |  |  |  |  | Brgy. Elizalde, Maco | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Camanlangan, New Bataan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Bataan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Bongbong, Pantukan (OPPAP-PAMANA) |  |  |  |  | Brgy. Bongbong, Pantukan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Monkayo (OPPAP-PAMANA) |  |  |  |  | Brgy. Poblacion, Monkayo | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Laak (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Laak | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Mabini (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Mabini | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. New Panay, Maragusan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Panay, Maragusan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Ngan, Compostela (OPPAP-PAMANA) |  |  |  |  | Brgy. Ngan, Compostela | 350000 |  |  | 0% |  | Procurement on process
Tablea Processing & Marketing Enterprise (PRDP-I-REAP) |  |  |  |  | Maragusan | 338000 |  |  | 100% | 338000 | Utilized
Camp Manuel Yan Eco-Tourism & Tribal Park Dev't. (TIEZA) |  |  |  |  | Mawab | 3000000 |  |  | 0% |  | Procurement on process
COMVAL Farm Agri-Eco-Tourism Development (TIEZA) Pasian, Monkayo |  |  |  |  | Pasian, Monkayo | 5000000 |  |  | 0% |  | Procurement on process
Other Special Projects (Provincial Counterpart) | [5 empty] | 2480689 |  |  | 0% |  | Procurement on process
Completion of Health Center Brgy. Magading, Nabunturan |  |  |  |  | Magading, Nabunturan | 220000 |  |  | 0% |  | Declared Savings
Completion of Mp-Bldg. (Madrash) Tunga, Magnaga |  |  |  |  | Magnaga | 160000 |  |  | 64.04% | 102464.5 | 90% On-going
Construction of Drainage at Purok Kauswagan, Purok Bagong, Lipunan, and
Purok Maga Chapoy Brgy. Mapawa, Maragusan |  |  |  |  | Brgy. Mapawa, Maragusan | 628053 |  |  | 0% |  | Procurement on process
Completion of Community Activity Center of Brgy. San Jose, Compostela |  |  |  |  | Brgy. San Jose, Compostela | 300000 |  |  | 0% |  | For change in Nomenclature from completion to const'n.
Rehabilitation of Water System from Purok 1-6, Brgy. Ampawid, Laak |  |  |  |  | Brgy. Ampawid, Laak | 500000 |  |  | 0% |  | POW approved. For 5th Amendatory
Renovation of Multi-Purpose Building in Special Brgy. Libuton, laak |  |  |  |  | Brgy. Libuton, Laak | 500000 |  |  | 0% |  | Procurement on process
Completion of Brgy. Tribal Council Building of Brgy. Cabuyoan, Mabini |  |  |  |  | Brgy. Cabuyoan, Mabini | 500000 |  |  | 0% |  | Cancelled
Construction of Protection Dike & Dessilting of Liboton River at Prk 2A |  |  |  |  | Brgy. Salvacion, Monkayo | 1000000 |  |  | 37.5% | 375000 | Procurement on process
Construction of Hanging Bridge at Purok 4 Brgy. Upper Ulip, Monkayo |  |  |  |  | Brgy. Upper Ulip, Monkayo | 1885193 |  |  | 2.818% | 53116.78 | Procurement on process
Concreting of Brgy. Road Brgy. Bankerohan Sur,Montevista |  |  |  |  | Brgy. Sur Montevista | 1000000 |  |  | 25.1% | 251041.56 | POW approved. For 5th Amendatory
Enhancement of Banana Cardava Consolidation and Marketing, New Bataan |  |  |  |  | New Bataan | 790000 |  |  | 0% |  | Procurement on process
Village Level Rubber Smoke Sheet Processing, Monkayo |  |  |  |  | Monkayo | 838000 |  |  | 0% |  | Procurement on process
W/S Improvement of Sitio Lawaan, Brgy. Kingking, Pantukan (oppap-pamana) |  |  |  |  | Brgy. Kingking, Pantukan | 1050000 |  |  | 0% |  | Procurement on process
Sub - Total | [5 empty] | 74984223.61 |  |  | 2397% | 16917396.08
[7 empty] | DATE STARTED |  | PROJECT STATUS
[8 empty] | TARGET |  | TOTAL
[8 empty] | COMPLETION | % OF | COST INCURRED
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST |  | DATE | COMPLETION | TO DATE
8917 (MOOE)
ECONOMIC DEVELOPMENT:
| Maintenance of roads/bridges - District 1 |  |  |  | Provincewide | 25107500 | 2017-01-03 | 2017-12-29 | 63.31% | 15895955.44 | On-going
| Maintenance of roads/bridges - District 2 |  |  |  | Provincewide | 23677846 | 2017-01-03 | 2017-12-29 | 81.11% | 19204679.22 | On-going
8918 (C.O)
| Construction and Heavy Equipment |  |  |  | Provincewide | 65000000 |  |  | 99.69% | 64800000 | Purchased Heavy Equipment
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
|  | Interest Expenses |  |  |  | 16228749 |  |  | 72.92% | 11834330.44 | Paid to Land Bank of the Phils.
|  | Loans Payable |  |  |  | 62564884 |  |  | 100% | 62564883.25 | Paid to Land Bank of the Phils.
|  |  | Sub - Total |  |  | 192578979 |  |  | 90.51% | 174299848.35
Grand Total | [5 empty] | 267563202.61 |  |  | 71.47% | 191217244.43
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  |  | As to Appropriation/Obligation | [6 empty] | Approved:
|  |  | EVA JEAN S. LICAYAN |  |  |  |  | JAYVEE TYRON L. UY
|  |  | Provincial Budget Officer |  |  |  |  | Governor

## Sheet1
40000000
1080000
905000
1000000
500000
750000
500000
1300000
1300000
1300000
1300000
500000
370000
875000
880000
625000
705000
58000
1000000
710000
1565000
1665000
1870000
1020000
985000
1405000
2260000
1490000
1890000
910000
1000000
645000
755000
810000
795000
1000000
1500000
5000000
1000000
1500000
1000000
1000000
1000000
5000000
2000000
1000000
1500000
700000
2500000
700000
2500000
700000
500000
500000
500000
147933.82
231546.6
149098.67
249273.02
221137.31
98784.86
118685.62
8355000
700000
116094459.9