## SHEET (hidden)
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of March 31, 2019
PROGRAM OR PROJECT |  |  |  | LOCATION |  | DATE STARTED |  | OBLIGATION
[5 empty] | TOTAL COST |  | TARGET | % OF | TOTAL | REMARKS
[5 empty] | Appropriation |  | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[7 empty] | DATE | APPROPRIATION | TO DATE
Annual Budget
SOCIAL DEVELOPMENT:
1918 (C.O)
Construction of Gym, Purok 2, Poblacion, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Construction of Gym, Mangayon NHS, Brgy. Mangayon, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Concreting of Road going to Valderama ES & NHS, Brgy. Ngan, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | Purchase Request on Process
Improvement of Water System, Brgy. Babag, Monkayo |  |  |  | Monkayo | 1200000 |  |  | 0% | 0 | Program of Works for Approval
Construction of Brgy. Stage, Brgy. Kao, Nabunturan |  |  |  | Nabunturan | 850000 |  |  | 0% | 0 | Purchase Request on Process
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  |  | New Bataan | 3000000 |  |  | 0% | 0 | For change in nomenclature from renovation to construction
Rehabilitation of Level II Water System, Brgy. Belmonte, Laak |  |  |  | Laak | 1500000 |  |  | 0% | 0 | For Detailed Engineering Design
Construction of Gym, Brgy. Poblacion, Maco |  |  |  | Maco | 5000000 |  |  | 0% | 0 | CONTRACT. Purchase Request on Process
Construction of Water System, Brgy. Taglawig, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0 | Program of Works on process.
Construction of Gym, Sitio Boringot, Brgy. Napnapan, Pantukan |  |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym, Sitio Panganason, Brgy, Kingking, Pantukan |  |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym Brgy. Tagdangua, Pantukan |  |  |  | Pantukan | 4000000 |  |  | 0% | 0 | For verification of project location. Waiting for brgy. captain's recommendation
Completion of Multi-purpose Building, Brgy Kingking, Pantukan NHS |  |  |  | Pantukan | 2000000 |  |  | 0% | 0 | Purchase Request on Process
Completion of Multi-purpose Building, Brgy. Kingking CES. Pantukan |  |  |  | Pantukan | 1000000 |  |  | 0% | 0 | Purchase Request on Process
Renovation of Dry Market, Brgy. Poblacion, Monkayo |  |  |  | Monkayo | 3000000 |  |  | 0% | 0
Construction of Brgy. Del Pilar Gym, Brgy. Del Pilar, Mabini |  |  |  | Mabini | 3000000 |  |  | 0% | 0
Development of Eco- Tourism Park Phase 2, Pantukan |  |  |  | Pantukan | 5000000 |  |  | 0%
Construction of Brgy. Stage, Brgy. Nuevo Iloco, Mawab |  |  |  | Mawab | 850000 |  |  | 0% | 0
Purchase of Lot for Happy Village, Brgy. Nueva Visayas, Mawab |  |  |  | Mawab | 2000000 |  |  | 0% | 0
Purchase of lot for the Expansion of Compostela Valley Provincial Hospitals |  |  |  |  | 3000000 |  |  | 0% | 0
Purchase of lot for the Development of Provincial Sports Complex |  |  |  |  | 12000000 |  |  | 0% | 0
Sub - Total Social Development |  |  |  |  | 66400000 |  |  |  | 0
ECONOMIC DEVELOPMENT:
1918 (MOOE)
Provincial Counterpart for Special Projects |  |  |  |  | 26719272.38 |  |  | 0% | 0
8917 (CO)
Rehabilitation Of Provincial Roads/ Bridges - District 1 |  |  |  | Provincewide | 28917741 |  |  | 4.801% | 1388279.87 | 4.80% Accomplished
Rehabilitation Of Provincial Roads/ Bridges - District 2 |  |  |  | Provincewide | 28584329 |  |  | 10.49% | 2999297.21 | 10.49% Accomplished
Rehabilitation of Farm-to-Market Roads (FMRS) - Provincewide |  |  |  | Provincewide | 5000000 |  |  | 0% | 0
Sub - Total Economic Development |  |  |  |  | 89221342.38 |  |  |  | 4387577.08
OTHER SERVICES:
1918 (CO)
Construction of Multi-Purpose Building - Provincewide |  |  |  | Provincewide | 1800000 |  |  | 0% | 0
Rehabilitation of Water System |  |  |  |  | 5000000 |  |  | 0% | 0
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  |  | 18109696.62 |  |  | 67.8% | 12279081.78 | Paid to Land Bank
| Loans Payable |  |  |  | 114338961 |  |  | 42.51% | 48605518.53 | Paid to Land Bank
Sub - Total Other Purposes |  |  |  |  | 139248657.62 |  |  |  | 60884600.31
Total Annual Budget |  |  |  |  | 294870000 |  |  |  | 65272177.39
Supplemental Budget No. 1
1918 (C.O)
Completion of Covered Court - Kinuban, Maco |  |  |  | Maco | 66304.34 |  |  | 0% | 0
Const. of PDEA MP Bldg., PPO-Nabunturan |  |  |  | Nabunturan | 62666.01 |  |  | 0% | 0
Imp. of MP Building- Maragusan |  |  |  | Maragusan | 5000000 |  |  | 0% | 0
Const. of Covered Court - Tagugpo NHS |  |  |  | Pantukan | 1150000 |  |  | 0% | 0
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  |  | New Bataan | 2000000 |  |  | 0% | 0
Completion of Municipal Tribal Hall, Pantukan |  |  |  | Pantukan | 2500000 |  |  | 0% | 0
Imp. of MP Bulding (Women Crisis Center), Brgy. Cabidianan, Nabunturan |  |  |  | Nabunturan | 3000000 |  |  | 0% | 0
Const. of MP Building (Bahay Pag-Asa) |  |  |  |  | 1000000 |  |  | 0% | 0
Const. of Gym, Brgy. Teresa, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0
Const. of PDEA MP Bldg., PPO-Nabunturan- Phase II |  |  |  | Nabunturan | 2500000 |  |  | 0% | 0
Const. of Covered Court - Kidawa, Laak |  |  |  | Laak | 220000 |  |  | 0% | 0
Conc. of Road with Drainage Component, Brgy. Cabidianan, Nabunturan |  |  |  | Nabunturan | 2833114.38 |  |  | 0% | 0
Conc. of Junction Nat'l Highway - Purok 2 to PRC, Brgy. Sta. Maria |  |  |  | Nabunturan | 1486992.37 |  |  | 0% | 0
Const. of Brgy. Stage, Brgy. Nueva Visayas, Mawab |  |  |  | Mawab | 850000 |  |  | 0% | 0
Imp. of Water System-Coronobe, Maragusan |  |  |  | Maragusan | 489400 |  |  | 0% | 0
Const. of WS, Brgy. Del Pilar, Mabini |  |  |  | Mabini | 3000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Tagnocon, Nabunturan |  |  |  | Nabunturan | 3000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Kinuban, Maco |  |  |  | Maco | 5000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Panibasan, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0
Imp. of WS-Brgy. Babag, Monkayo |  |  |  | Monkayo | 427500 |  |  | 0% | 0
Const. of Health Center-Mapaang, Maco |  |  |  | Maco | 1500000 |  |  | 0% | 0
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  |  | 3557622.9 |  |  | 0% | 0
Total Supplemental Budget No. 1 |  |  |  |  | 45643600 |  |  |  | 0
Grand Total |  |  |  |  | 340513600 |  |  |  | 65272177.39
Summary: | [7 empty] | %of Obligation/
[5 empty] | Appropriation |  |  | Appropriation | Obligation
| 1918 | Social Development |  |  | 115285977.1 |  |  | 0% | 0
| 8917 | Economic Development |  |  | 89221342.38 |  |  | 4.918% | 4387577.08
| 9911 | Financial Expenses |  |  | 136006280.52 |  |  | 44.77% | 60884600.31
|  | Grand Total |  |  | 340513600 |  |  | 19.17% | 65272177.39
|  |  |  | check | 340513600
0
65272177.39
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  | As to Appropriation/Obligation |  |  | As to Project Status: |  |  |  | Approved:
|  | EVA JEAN S. LICAYAN, ENP, REB, MPA |  | ROMEO B. CELESTE, ENP |  | ENGR. RODERICK M. DIGAMON |  |  | JAYVEE TRON L. UY, MPA
|  | Provincial Budget Officer |  | Provincial Planning & Development Office |  | Provincial Engineer's Office |  |  | Governor
282039226.9
-58474373.1

## PRINT
Republic of the Philippines
Province of Davao De Oro
Provincial Budget office
2F, Executive Building, Provincial Capitol, Cabidianan, Nabunturan, Davao De Oro | [11 empty] | yellow social
20% COMPONENT OF THE IRA UTILIZATION | [11 empty] | white economic
As of December 31, 2020 | [11 empty] | green environmental
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST APPROPRIATION | DATE STARTED | TARGET COMPLETION DATE | OBLIGATION
[9 empty] | % OF | TOTAL | REMARKS
[9 empty] | OBLIGATION/ | COST INCURRED | (PROJECT STATUS)
[9 empty] | APPROPRIATION | TO DATE
ANNUAL BUDGET
SOCIAL DEVELOPMENT:
1. Completion of Multipurpose Building (Brgy. Health |  |  |  |  | Mabini | 350000 | 2020-09-22 | 2020-11-15 | 81.49% | 285224.13 | Completed on November 15, 2020
Station), Brgy. Cadunan, Mabini
2. Completion of Multipurpose Building, Brgy. Langtud, Laak |  |  |  |  | Laak | 1500000 | 2020-04-10 | 2020-09-09 | 96.53% | 1447965.46 | CONTRACT Blurex Construction & Supply. Completed on September 1, 2020.
3. Concreting of Road From Tagbarus Crossing to |  |  |  |  | Maco | 2000000 | 2020-12-03 | 2021-03-09 | 31.98% | 639613.31 | On-going.
Tagbarus ES, Maco
4. Concreting of Road, Brgy. Mainit, Nabunturan |  |  |  |  | Nabunturan | 14000000 | 2020-07-02 | 2021-01-18 | 98.95% | 13853154.99 | CONTRACT. Legacy Construction Corp. On-going.
5. Concreting of Road, Poblacion Laak |  |  |  |  | Laak | 0 |  |  |  | 0 | Abandoned. Project duplication with DPWH. realigned for SB No. 4, 2020.
6. Construction of Hanging Bridge, Purok 6, |  |  |  |  | Laak | 3000000 | 07/16/2020 | 2020-11-09 | 92.68% | 2780283.94 | CONTRACT. LLM Unified Builders & Trading Corp. Completed on November 6, 2020
Tawin-Tawin, Brgy. Antonio, Laak
7. Construction of Multipurpose Building (Brgy. |  |  |  |  | Laak | 2000000 | 2020-04-10 | 2020-09-12 | 97.84% | 1956880.42 | CONTRACT Blurex Construction & Supply. Completed September 1, 2020.
Health Center), Brgy. Kibaguio, Laak
8. Construction of Multipurpose Building (Day Care |  |  |  |  | Laak | 500000 |  |  | 0% | 0 | CONTRACT. Bidded.
Center), Brgy. Datu Davao, Laak
9. Construction of Multipurpose Building (Day Care |  |  |  |  | Maco | 1500000 | 2020-07-02 | 2020-11-08 | 95.05% | 1425788.06 | CONTRACT. MICAH Construction & Supply. Completed on November 6, 2020.
Center), Brgy. Dumlan, Maco
10. Construction of Multipurpose Building (Day Care |  |  |  |  | Laak | 1500000 | 2020-04-10 | 2020-09-11 | 99.77% | 1496503.21 | CONTRACT Blurex Construction & Supply. Completed September 11, 2020.
Center), Brgy. Il Papa, Laak
11. Construction of Multipurpose Building (Day Care |  |  |  |  | Pantukan | 1500000 | 2020-07-02 | 2020-10-25 | 99.59% | 1493795.76 | CONTRACT. LLM Unified Builders & Trading Corp. Completed on October 20, 2020.
Center), Brgy. Tambungon, Pantukan
12. Construction of Multipurpose Building (Day Care |  |  |  |  | Monkayo |  |  |  |  | 0 | Abandoned. Declared Savings for SB No. 1.
Center), NHA Village Brgy. Banlag, Monkayo
13. Construction of Multipurpose Building (Day Care |  |  |  |  | Laak |  |  |  |  | 0 | Abandoned. Declared Savings for SB No. 1.
Center), Special Brgy. Bayanihan, Laak
14. Construction of Multipurpose Building (H.E. |  |  |  |  | Maco | 3000000 | 07/16/2020 | 12/19/2020 | 81.75% | 2452617.67 | CONTRACT. MICAH Construction & Supply. On-Going.
Building, Taglawig NHS), Brgy. Taglawig, Maco
15. Construction of Multipurpose Building at Bantacan |  |  |  |  | New Bataan | 4000000 | 04/17/2020 | 10/26/2020 | 2.525% | 100983 | CONTRACT. Davao Santhony Builders. Completed on October 22, 2020.
NHS, Bantacan, New Bataan
16. Construction of Multipurpose Building at Bawani |  |  |  |  | Mawab | 2000000 | 03/27/2020 | 10/18/2020 | 97.03% | 1940607.69 | CONTRACT. LLM Unified Builders and Trading Corp. Completed on October 11, 2020.
E/S, Bawani, Mawab
17. Construction of Multipurpose Building at Gabi |  |  |  |  | Compostela | 4000000 | 03/27/2020 | 2021-01-08 | 98.5% | 3939954.81 | CONTRACT Blurex Construction & Supply. On-Going.
NHS, Brgy. Gabi, Compostela
18. Construction of Multipurpose Building at |  |  |  |  | Maco | 2000000 | 2020-07-02 | 2020-10-06 | 99.09% | 1981745.46 | CONTRACT. MICAH Construction & Supply. Completed on October 19, 2020.
Kabarucanan E/S, Bgry. Malamodao, Maco
19. Construction of Multipurpose Building at Kolehiyo |  |  |  |  | Pantukan | 2000000 | 2020-07-02 | 2020-10-27 | 82.26% | 1645217.97 | CONTRACT. LLM Unified Builders & Trading Corp. Completed on October 22, 2020.
ng Pantukan, Pantukan
20. Construction of Multipurpose Building at Mabuhay |  |  |  |  | Laak | 4000000 | 04/17/2020 | 2020-12-19 | 98.55% | 3941899.22 | CONTRACT. Two Degrees Construction & Supply. Completed on December 17, 2020
NHS, Brgy. Mabuhay Laak
21. Construction of Multipurpose Building at Manat |  |  |  |  | Nabunturan | 4000000 | 04/17/2020 | 2021-01-04 | 99.24% | 3969652.65 | CONTRACT Blurex Construction & Supply. On-Going. | wala sa project status
NHS, Brgy. Manat, Nabunturan
22. Construction of Multipurpose Building at New |  |  |  |  | Montevista | 2000000 | 2020-07-02 | 09/21/2020 | 96.29% | 1925752.12 | CONTRACT. LLM Unified Builders & Trading Corp. Completed on August 27, 2020.
Calape E/S, Brgy. New Calape, Montevista
23. Construction of Multipurpose Building at San |  |  |  |  | Compostela | 4000000 | 03/27/2020 | 2020-12-12 | 96.56% | 3862322.49 | CONTRACT Blurex Construction & Supply. On-Going.
Miguel NHS, Compostela
24. Construction of Multipurpose Building, Brgy. Anibongan, Maco |  |  |  |  | Maco | 4000000 | 2020-07-02 | 2020-12-27 | 96.21% | 3848483.26 | CONTRACT. MICAH Construction & Supply. On-Going.
25. Construction of Multipurpose Building, Brgy. Babag, Monkayo |  |  |  |  | Monkayo | 4000000 | 2020-07-02 | 2021-01-24 | 99.55% | 3982095.97 | CONTRACT Blurex Construction & Supply. On-Going.
26. Construction of Multipurpose Building, Brgy. Binasbas, Laak |  |  |  |  | Laak | 1000000 | 2020-04-10 | 2020-08-20 | 98.88% | 988838.78 | CONTRACT Blurex Construction & Supply. Completed August 20, 2020.
27. Construction of Multipurpose Building, Brgy. Hijo, Maco |  |  |  |  | Maco | 1000000 | 2020-07-02 | 2020-11-03 | 2.943% | 29431.1 | CONTRACT. MICAH Construction & Supply. Completed on November 3, 2020.
28. Construction of Multipurpose Building, Brgy. Sta. Emilia, Laak |  |  |  |  | Laak | 4000000 | 2020-07-02 | 2020-10-23 | 35.82% | 1432626.84 | CONTRACT Blurex Construction & Supply. Completed on October 21, 2020.
29. Construction of Multipurpose Building, Brgy. Tandawan, |  |  |  |  | New Bataan | 1500000 | 04/17/2020 | 07/23/2020 | 2.491% | 37357.55 | CONTRACT. Davao Santhony Builders. Completed on July 23, 2020.
New Bataan
30. Construction of Multipurpose Building, Purok 13, Poblacion, |  |  |  |  | Compostela | 3000000 | 03/27/2020 | 1122/2020 | 99.51% | 2985237.24 | CONTRACT Blurex Construction & Supply. Completed on November 20, 2020.
Compostela
31. Construction/Upgrading of Multipurpose Building (Women |  |  |  |  | Nabunturan | 2000000 |  |  | 93.11% | 1862273.08 | On-going.
Crisis Building) Phase II, Cabidianan, Nabunturan
32. Development of Kalayaan Center, Brgy. Libasan, Nabunturan |  |  |  |  | Nabunturan | 1700000 | 2020-11-03 | 2021-02-01 | 55.59% | 945006.13 | On-going.
33. Improvement/Expansion of Multi Purpose Building, |  |  |  |  | Pantukan | 1000000 | 2020-10-26 | 2021-02-01 | 55.17% | 551651.92 | On-going.
Brgy, Matiao, Pantukan
34. Provincial Counterpart to Special Projects: | [10 empty] | For implementation.
|  |  |  | AB 2020 |  | 383236.65 |  |  | 0% | 0
|  |  |  | SB No. 5 |  | 935281.2 |  |  | 0% | 0
35. Upgrading/Improvement of Multipurpose Building, Mabini |  |  |  |  | Mabini | 0 |  |  |  | 0 | realigned for SB No. 4, 2020.
Sub - Total Social Development | [5 empty] | 83368517.85 |  |  |  | 67802964.23
ECONOMIC DEVELOPMENT:
36. Rehabilitation of Provincial Roads/ Bridges - District 1 |  |  |  |  | Provincewide | 28917741 |  |  | 89.94% | 26009145.65 | On-going.
37. Rehabilitation of Provincial Roads/ Bridges - District 2 |  |  |  |  | Provincewide | 28584329 |  |  | 94.32% | 26960790.12 | On-going.
38. District I - Rehabilitation of FMR, Brgy. Bahi Road, Maragusan |  |  |  |  | Maragusan | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
39. District I - Rehabilitation of FMR, Brgy. |  |  |  |  | New Bataan | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
Camanlangan, New Bataan
40. District I - Rehabilitation of FMR, Brgy. |  |  |  |  | Maragusan | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
Langawisan Road, Maragusan
41. District I - Rehabilitation of FMR, Brgy. Las |  |  |  |  | Pantukan | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
Arenas, Pantukan
42. District I - Rehabilitation of FMR, Brgy. |  |  |  |  | New Bataan | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
Magangit, New Bataan
43. District I - Rehabilitation of FMR, Brgy. Mainit, Nabunturan |  |  |  |  | Nabunturan | 1900000 | 2020-05-11 | 6/25/2020 | 80.13% | 1522452.39 | Completed on October 30, 2020.
44. District I - Rehabilitation of FMR, Brgy. Manat, Nabunturan |  |  |  |  | Nabunturan | 1900000 | 2020-03-02 | 04/17/2020 | 84.04% | 1596685.6 | Completed on September 15, 2020.
45. District I - Rehabilitation of FMR, Brgy. Mt. Diwata, Monkayo |  |  |  |  | Monkayo | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
46. District I - Rehabilitation of FMR, Brgy. Ngan, Compostela |  |  |  |  | Compostela | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
47. District I - Rehabilitation of FMR, Brgy. Paloc Road, |  |  |  |  | Maragusan | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
Maragusan
48. District I - Rehabilitation of FMR, Brgy. Parasanon Road, |  |  |  |  | Maragusan | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
Maragusan
49. District I - Rehabilitation of FMR, Brgy. San Vicente, |  |  |  |  | Montevista | 1900000 | 2020-10-05 | 2020-11-18 | 63.02% | 1197310.5 | On-going.
Montevista
50. District I - Rehabilitation of FMR, Sitio Panansalan, Brgy. |  |  |  |  | Compostela | 0 |  |  |  | 0 | Abandoned. realigned for SB No. 4, 2020.
Ngan, Compostela
51. District II - Rehabilitation of Brgy. Ampawid-brgy. Buhi FMR, |  |  |  |  | Laak | 1747852 | 2020-04-06 | 08/18/2020 | 94.06% | 1644050.11 | Completed on July 24, 2020.
Laak
52. District II - Rehabilitation of Brgy. Cabuyuan FMR, Laak |  |  |  |  | Laak | 0 |  |  |  | 0 | Change Nomenclature from Laak to Mabini SB No. 7.
53. District II - Rehabilitation of Brgy. Gubatan FMR, Maco |  |  |  |  | Maco | 908350 | 02/14/2020 | 04/16/2020 | 58.16% | 528262.19 | Completed on April 15, 2020.
54. District II - Rehabilitation of Brgy. Kapatagan-brgy. Dalimdim |  |  |  |  | Laak | 908350 | 07/27/2020 | 2020-10-01 | 97.17% | 882679 | Completed on September 30, 2020.
FMR, Laak
55. District II - Rehabilitation of Brgy. Kiokmay-Brgy. |  |  |  |  | Laak | 908350 | 2020-02-26 | 2020-04-30 | 84.29% | 765628.76 | Completed on April 30, 2020.
Aguinaldo FMR, Laak
56. District II - Rehabilitation of Brgy. Panangan FMR, Maco |  |  |  |  | Maco | 1207676 | 02/28/2020 | 2020-05-04 | 96.73% | 1168180.06 | Completed on June 30, 2020.
57. Loans Payable - Domestic | [5 empty] | 93953759.15 |  |  | 100% | 93953759.15 | Paid to Landbank.
58. Interest Expenses | [5 empty] | 22574534.2 |  |  | 63.55% | 14345176.97 | Paid to Landbank.
Sub - Total Economic Development | [5 empty] | 185410941.35 |  |  |  | 170574120.5
ENVIRONMENTAL MANAGEMENT:
59. Construction of Water System at Kalayaan Center, |  |  |  |  | Nabunturan | 3000000 |  |  | 0% | 0 | CONTRACT. Awarded to Blurex Construction & Supply.
Brgy. Libasan, Nabunturan
60. Construction of Water System at Liwanag Center, |  |  |  |  | Nabunturan | 3000000 | 2020-10-08 | 2021-02-07 | 0.1297% | 3889.63 | CONTRACT. Blurex Construction & Supply. On-going.
Brgy. Libasan, Nabunturan
61. Construction of Mini-warehouse Facility - Naboc, Monkayo |  |  |  |  | Monkayo | 250000 |  |  | 50.44% | 126103 | On-going.
62. Construction of Mini-warehouse Facility - P-4, |  |  |  |  | New Bataan | 250000 |  |  | 50.44% | 126103 | On-going.
Panag, New Bataan
63. Construction of Multi-commodity Solar Dryer - |  |  |  |  | Montevista | 125000 |  |  | 99.34% | 124174 | On-going.
Banag-banag, Montevista
64. Construction of Multi-commodity Solar Dryer - |  |  |  |  | Pantukan | 125000 |  |  | 99.34% | 124174 | On-going.
Napnapan, Pantukan
65. Construction of Multi-commodity Solar Dryer - |  |  |  |  | Nabunturan | 125000 |  |  | 99.34% | 124174 | On-going.
P-3, Antequera, Nabunturan
66. Construction of Multi-commodity Solar Dryer - P-6 |  |  |  |  | Montevista | 125000 |  |  | 99.34% | 124174 | On-going.
San Jose, Montevista
Sub - Total Environmental Management | [5 empty] | 7000000 |  |  |  | 752791.63
TOTAL ANNUAL BUDGET | [5 empty] | 275779459.2 |  |  |  | 239129876.36
SUPPLEMENTAL BUDGET NO. 1
SOCIAL DEVELOPMENT:
67. Provision for Food and Non-food Items Assistance
| for the Affected Households- Food Supplies Expenses |  |  |  | Provincewide | 25863550 |  |  | 99.99% | 25862000 | Delivered to beneficiaries.
TOTAL SUPPLEMENTAL BUDGET NO. 1 | [5 empty] | 25863550 |  |  |  | 25862000
SUPPLEMENTAL BUDGET NO. 3
SOCIAL DEVELOPMENT:
68. Provision for Food Items Assistance for the
| Affected Households - Food Supplies Expenses |  |  |  | Provincewide | 22389064.71 |  |  | 99.99% | 22387500 | On-going.
69. Procurement of Hospital Equipment | [5 empty] | 9200000 |  |  | 99.91% | 9192000 | Delivered to Hospital.
TOTAL SUPPLEMENTAL BUDGET NO. 3 | [5 empty] | 31589064.71 |  |  |  | 31579500
SUPPLEMENTAL BUDGET NO. 4
SOCIAL DEVELOPMENT:
70. Completion of Health Center, Brgy. Mapaang, Maco |  |  |  |  | Maco | 1000000 |  |  | 0% | 0 | CONTRACT. Pre-bidded.
71. Completion of Liwanag (Drug Treatment/ Rehabilitation Clinic), |  |  |  |  | Nabunturan | 2800000 |  |  | 66.66% | 1866376.79 | Purchase order on process.
Brgy. Libasan, Nabunturan
72. Completion of Multipurpose Building (Day Care Center), |  |  |  |  | Pantukan | 650000 |  |  | 0% | 0 | CONTRACT. Awarded to MICAH Construction and Supply.
Brgy. Napnapan, Pantukan
73. Completion of Multipurpose Building (HE Building), |  |  |  |  | Laak | 700000 |  |  | 56.99% | 398918.09 | Purchase order on process.
Brgy. Kibaguio, Laak
74. Completion of Multipurpose Building (Stage) at |  |  |  |  | Montevista | 350000 |  |  | 47.21% | 165245.93 | Purchase order on process.
Montevista CES, Poblacion, Montevista
75. Completion of Multipurpose Building at Kingking |  |  |  |  | Pantukan | 500000 |  |  | 62.85% | 314254 | Purchase order on process.
CES, Pantukan (Additional Appropriation)
76. Completion of Multipurpose Building, Capitol Complex, |  |  |  |  | Nabunturan | 700000 |  |  | 35.42% | 247972.3 | Purchase order on process.
Nabunturan
77. Completion of Multipurpose Hall At Brgy. Casoon, Monkayo |  |  |  |  | Monkayo | 400000 |  |  | 62.46% | 249856.8 | Purchase order on process.
78. Construction of Brgy. Health Center, Brgy. |  |  |  |  | Laak | 1000000 |  |  | 0% | 0 | CONTRACT. Awarded to Blurex Construction & Supply.
Kibaguio, Laak – Phase II
79. Construction of Isolation Room at Training Center, COMVAL |  |  |  |  | Monkayo | 500000 |  |  | 0% | 0 | Program of works for approval.
Farm, Pasian, Monkayo
80. Construction of Multipurpose Building (Day Care Center), |  |  |  |  | Montevista | 300000 |  |  | 0% | 0 | CONTRACT. Pre-bidded.
Brgy. Camansi, Montevista – Phase II
81. Construction of Multipurpose Building (Day Care Center), |  |  |  |  | Laak | 300000 |  |  | 0% | 0 | CONTRACT. Bidded.
Brgy. Datu Davao, Laak – Phase II
82. Construction of Potable Water System, Brgy. |  |  |  |  | Nabunturan | 2400000 |  |  | 0% | 0 | CONTRACT. Pre-bidded.
Tagnocon, Nabunturan (Phase II)
83. Construction of Water System, Brgy. Del Pilar, |  |  |  |  | Mabini | 4350000 |  |  | 0% | 0 | CONTRACT. Pre-bidded.
Mabini – Phase II
84. Purchase of Lot for the Establishment of Kalayaan |  |  |  |  | Nabunturan | 410164.8 |  |  | 41.46% | 170050 | On-going.
Center in Barangay Libasan, Nabunturan
85. Rehabilitation of Davao De Oro Provincial |  |  |  |  | Montevista | 800000 |  |  | 0% | 0 | CONTRACT. Awarded to PMMGS Construction Corp.
Hospital (Installation of Cistern Tank, Feeder
Line & Control of Fire Protection System), Montevista
86. Rehabilitation of Davao De Oro Provincial |  |  |  |  | Pantukan | 1000000 |  |  | 88.33% | 883300 | CONTRACT. Awarded to MICAH Construction and Supply.
Hospital (Installation of Electrical System,
Airconditioning and Installation of Fan), Pantukan
87. Rehabilitation of Davao De Oro Provincial |  |  |  |  | Laak | 1200000 |  |  | 0% | 0 | CONTRACT. Awarded to Tagum Builders Contractors Corp.
Hospital (Installation of Feeder Line and Control
of Fire Protection System), Laak
88. Rehabilitation of Davao De Oro Provincial |  |  |  |  | Maragusan | 1100000 |  |  | 0% | 0 | CONTRACT. Awarded to FFJJ Construction.
Hospital (Installation of Feeder Line and Control
of Fire Protection System), Maragusan
89. Rehabilitation of Davao De Oro Provincial |  |  |  |  | Montevista | 450000 |  |  | 54.15% | 243664 | Purchase order on process.
Hospital (Repair of Comfort Rooms), Montevista
90. Rehabilitation of Multipurpose Building at Sta. |  |  |  |  | Nabunturan | 1000000 |  |  | 61.82% | 618209 | Purchase order on process.
Maria, Nabunturan
91. Upgrading/Improvement of Davao De Oro Provincial | [5 empty] | 1000000 |  |  | 48.26% | 482558.74 | Purchase order on process.
Rehabilitation Complex
Sub - Total Social Development | [5 empty] | 22910164.8 |  |  |  | 5640405.65
ECONOMIC DEVELOPMENT:
92. Rehabilitation of Cabinuangan-Magangit FMR, New Bataan |  |  |  |  | New Bataan | 6000000 |  |  | 1.696% | 101756.99 | CONTRACT. Bidded.
Sub - Total Economic Development | [5 empty] | 6000000 |  |  |  | 101756.99
TOTAL SUPPLEMENTAL BUDGET NO. 4 | [5 empty] | 28910164.8 |  |  |  | 5742162.64
SUPPLEMENTAL BUDGET NO. 5
ECONOMIC DEVELOPMENT:
93. Rehabilitation of Farm to Market Road at Sitio Calamucan, |  |  |  |  | New Bataan | 5000000 |  |  | 0% | 0 | Program of works for approval.
Brgy. Cabinuangan - Sitio Tubod, Brgy. Manurigao,
New Bataan, Davao de Oro
TOTAL SUPPLEMENTAL BUDGET NO. 5 | [5 empty] | 5000000 |  |  |  | 0
SUPPLEMENTAL BUDGET NO. 6
SOCIAL DEVELOPMENT:
94. Construction of Municipal Tribal Hall, Phase II, Pantukan |  |  |  |  | Pantukan | 2500000 |  |  | 0% | 0 | Program of works on process.
TOTAL SUPPLEMENTAL BUDGET NO. 6 | [5 empty] | 2500000 |  |  |  | 0
SUPPLEMENTAL BUDGET NO. 7
ECONOMIC DEVELOPMENT:
95. District II - Rehabilitation of Brgy. Cabuyuan FMR, Mabini |  |  |  |  | Mabini | 1469422 | 2020-03-05 | 2021-04-12 | 81.26% | 1194030.46 | On-going.
TOTAL SUPPLEMENTAL BUDGET NO. 7 | [5 empty] | 1469422 |  |  |  | 1194030.46
Summary: | [8 empty] | % of Obligation/ |  |  | 260213244.01 | 260213244.01 | zero means no changes to obligations
[6 empty] | Appropriation |  |  | Appropriation | Obligation
|  | Social Development |  |  |  | 166231297.36 |  |  | 78.74% | 130884869.88
|  | Economic Development |  |  |  | 197880363.35 |  |  | 86.86% | 171869907.95
|  | Environmental Management |  |  |  | 7000000 |  |  | 10.75% | 752791.63
|  | Grand total |  |  |  | 371111660.71 |  |  | 81.78% | 303507569.46
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | as to Appropriation/Obligation: |  |  | as to Project Status: | [5 empty] | Approved:
|  |  | (SGD.) |  | (SGD.) |  |  | (SGD.) |  |  | (SGD.)
|  | EVA JEAN S. LICAYAN, ENP, REB, MPA |  |  | ROMEO B. CELESTE, ENP |  | ENGR. RODERICK M. DIGAMON |  |  |  | JAYVEE TYRON L. UY, MPA
|  | Provincial Budget Officer |  |  | Provincial Planning & |  | Provincial Engineer |  |  |  | Governor
Development Officer
[6 empty] | 367266214.71 |  |  |  | 146370185.99
[6 empty] | -3845446 |  |  |  | -157137383.47

## roads and bridges (hidden)
d1 |  | d2
1406312.94 | 1 | 450666.82
346641.07 | 2 | 3691173.19
329338.25 | 3 | 1187823.25
860736.66 | 4 | 302357.89
754121.02 | 5 | 443858.29
665957.25 | 6 | 374428.06
544873.39 | 7 | 639808.52
1353782.24 | 8 | 1222449.7
1587558.73 | 9 | 961270.42
1551379.51 | 10 | 502575.03
1069370.6 | 11 | 358411.19
607875.22 | 12 | 375094.6
721191.34 | 13 | 146437.95
963298.57 | 14 | 236740.16
2760936.08 | 15 | 291795.83
1286500.07 | 16 | 1874149.59
870815.18 | 17 | 596713.11
418001.17 | 18 | 375020.62
1505817.84 | 19 | 394342.91
1238228.44 | 20 | 601211.95
359101.69 | 21 | 370613.91
256470.21 | 22 | 450447.22
1002796.15 | 23 | 33831.18
738974.46 | 24 | 560682.9
1238663.92 | 25 | 287876.96
245287.26 | 26 | 190649.67
287922.45 | 27 | 374932.65
649684.57 | 28 | 300551.75
576306.14 | 29 | 252591.74
454766.29 | 30 | 245486.18
291166.54 | 31 | 174550.8
656730.56 | 32 | 495228.2
262775.76 | 33 | 117163.28
| 34 | 299344.62
27863381.57 | 35 | 374976.44
| 36 | 104511.58
| 37 | 375108.65
| 38 | 1493740.5
| 39 | 97714.15
| 40 | 296397.92
| 41 | 1109651.47
| 42 | 370132.58
| 43 | 600755.37
| 44 | 798288.05
| 45 | 1130549.9
| 46 | 427997.11
| 47 | 900692.95
| 48 | 749249.09
28010045.9

## July-Sept. (hidden)
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST | DATE STARTED |  | OBLIGATION
[8 empty] | TARGET | % OF | TOTAL | REMARKS
[8 empty] | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[8 empty] | DATE | APPROPRIATION | TO DATE
1918 (MOOE)
SOCIAL DEVELOPMENT:
F/A Repair/Rehabilitation of Farm-to-Market Roads (FMR) |  |  |  |  | Provincewide | 5000000 |  |  | 0% |  | Program of works on process
F/A Provincial Counterpart for Special Programs/Projects |  |  |  |  | Provincewide | 10000000 |  |  | 0% |  | Program of works on process
F/A Repair/Rehabilitation of Water System |  |  |  |  | Provincewide | 4000000 |  |  | 0% |  | Program of works on process
Purchase of Various Sizes of HDPE Pipes
Distribution of Materials for Brgys. Magnaga, Bongbong, Matiao, Tambongon of Pantukan and Brgy. Pangi of Maco
F/A Construction/Purchase of Post Harvest Facilities |  |  |  |  | Provincewide | 1000000 |  |  | 0% |  | Procurement on process
F/A Completion of Multi-Purpose Building-Barangay Lahi, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Concreting of Barangay Road-Barangay Magcagong, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Acquisition of Dump Truck-Barangay New Manay, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Purok Multi-Purpose Center |  |  |  |  | Brgy. New Panay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Water System |  |  |  |  | Brgy. Talian, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. Mapawa, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. New Albay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Covered Court |  |  |  |  | Brgy. Mauswagon, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Multi-Purpose Building |  |  |  |  | Brgy. Coronobe, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Covered Court |  |  |  |  | Prk 1 Brgy. Paloc, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Purchase of Dump Truck |  |  |  |  | Laak | 2400000 |  |  | 0% |  | Procurement on process
F/A Construction of Covered Court |  |  |  |  | Brgy. Ceboleda, Laak | 1000000 |  |  | 76.27% | 762650.5 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Banbanon, Laak | 1000000 |  |  | 72.93% | 729340.48 | 20% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Bagong Silang, Laak | 1500000 |  |  | 71.54% | 1073131.28 | 15% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. New Bethlehem, Laak | 1000000 |  |  | 69.58% | 695782.73 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Kiokmay, Laak | 1000000 |  |  | 65.71% | 657073.29 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Cabuyuan, Mabini | 1000000 |  |  | 72.51% | 725068.58 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Salvacion, Mawab | 1000000 | 2017-06-27 | 2017-09-25 | 94.32% | 943242.52 | 30% 0n-going
Construction of Day Care Center- Sitio Cambodlot, San Miguel, Compostela |  |  |  |  | Compostela | 245446.21 | 2017-05-30 | 2017-08-18 | 90.62% | 222432.28 | 98% Temporarily Suspended.
Concreting of Road @ Bonifacio-Garcia St. Brgy. Poblacion, Compostela |  |  |  |  | Brgy. Compostela | 237240.2 | 2017-04-10 | 2017-05-05 | 95.16% | 225760.96 | Completed
Concreting of Road @ Emilio Aguinaldo St. Purok 1 |  |  |  |  | Brgy. Poblacion, Compostela | 206207.36 | 2017-05-02 | 2017-06-21 | 98.04% | 202175.97 | Completed
Concreting of Road from Brgy. Dauman to Brgy. Concepcion, Montevista |  |  |  |  | Brgy. Concepcion, Montevista | 1064369.3 | 2017-04-17 | 2017-08-25 | 96.26% | 1024555 | Completed
Concreting of Road Brgy. San Vicente, Montevista |  |  |  |  | Brgy. San Vicente, Montevista | 223652.46 | 2017-04-20 | 2017-06-20 | 97.43% | 217906.77 | Completed
Construction of Covered Court-Brgy. Cabacungan, Nabunturan |  |  |  |  | Brgy. Cabacungan, Nabunturan | 322320.39 | 2017-04-12 | 2017-07-27 | 57.83% | 186400.24 | Completed
Construction of Covered Court-Brgy. Basak (stage), Nabunturan |  |  |  |  | Nabunturan | 92762.56 | 2017-04-11 | 2017-05-24 | 99.2% | 92016.32 | Completed
F/A-Construction of Covered Court-Brgy. Mt. Diwata, Monkayo |  |  |  |  | Monkayo | 1000000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
Concreting of FMR, Purok 5, Tagaytay, Brgy. Mipangi, Nabunturan |  |  |  |  | Nabunturan | 267931.28 | 2017-05-02 | 2017-05-17 | 99.98% | 267886.12 | Completed
Concreting of Road from Junction National Highway to Purok 6 |  |  |  |  | Nabunturan | 1222342.98 | 2017-04-17 | 2017-08-15 | 55.44% | 677619.83 | 95% On-going
Concreting of Road at Brgy. Cabacungan, Nabunturan |  |  |  |  | Nabunturan | 576798.44 | 2017-04-12 | 2017-06-22 | 73.13% | 421799 | Completed
Concreting of Road from Junction Nat'l. H-way to Cabidianan Annex HS |  |  |  |  | Brgy. Nabunturan | 329035.58 | 2017-04-17 | 2017-07-05 | 95.32% | 313648.82 | Completed
Concreting of Road at Mapaang Section |  |  |  |  | Brgy. Mapaang, Maco | 212862.75 | 2017-05-16 | 2017-05-25 | 40.08% | 85316.88 | Completed
Construction of Multi-Purpose Building |  |  |  |  | Brgy. Poblacion, Mawab | 81822.86 | 2017-05-03 | 2017-06-07 | 71.44% | 58454.82 | 98% Temporarily Suspended.
Construction of Multi-Purpose Building (Council of Women) |  |  |  |  | Brgy. Las Arenas, Pantukan | 200030.48 | 2017-04-17 | 2017-06-20 | 63.25% | 126526.2 | 85% On-going
Construction of Tribal Hall |  |  |  |  | Brgy. Poblacion, Pantukan | 546787 | 2017-06-13 | 2017-10-06 | 35.96% | 196650.73 | 20% On-going
Construction of Multi-Purpose Building (Madrasah) |  |  |  |  | Tunga, Monkayo | 226099.1 | 2017-05-08 | 2017-07-18 | 55.51% | 125496.38 | 95% On-going
Construction of Multi-Purpose Building (ABC) |  |  |  |  | Compostela | 137322.6 | 2017-04-17 | 2017-06-15 | 98.16% | 134802.5 | Completed
Concreting of Road from Junction National H-way to Brgy. Hall |  |  |  |  | Bankerohan Sur, Montevista | 77881.34 | 2017-05-29 | 2017-06-13 | 94.37% | 73496.66 | Completed
Concreting of Road from Prk 8-Prk 7 to Junction National |  |  |  |  | Montevista | 420064.72 | 2017-04-17 | 2017-07-31 | 97.26% | 408538.38 | Completed
F/A Construction of Hanging Bridge (footbridge) Prk 9 |  |  |  |  | Salvacion, Monkayo | 650000 |  |  | 100% | 650000 | For Fund Transfer to Municipality (FTM)
F/A Construction of Slaughter House, Pantukan |  |  |  |  | Pantukan | 4700000 |  |  | 95.74% | 4500000 | For Fund Transfer to Municipality (FTM)
1918 (C.O)
Rehab. Of Brgy. Poblacion-Brgy. Naboc FMR, Monkayo (PRDP-BUILD) |  |  |  |  | Monkayo | 1358700 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Monkayo | 565505 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Maparat, Compostela | 521906 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Libasan, Nabunturan | 521902 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Linda, Nabunturan | 542264 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Kilagding, Laak | 543034 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Elizalde, Maco (OPPAP-PAMANA) |  |  |  |  | Brgy. Elizalde, Maco | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Camanlangan, New Bataan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Bataan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Bongbong, Pantukan (OPPAP-PAMANA) |  |  |  |  | Brgy. Bongbong, Pantukan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Monkayo (OPPAP-PAMANA) |  |  |  |  | Brgy. Poblacion, Monkayo | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Laak (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Laak | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Mabini (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Mabini | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. New Panay, Maragusan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Panay, Maragusan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Ngan, Compostela (OPPAP-PAMANA) |  |  |  |  | Brgy. Ngan, Compostela | 350000 |  |  | 0% |  | Procurement on process
Tablea Processing & Marketing Enterprise (PRDP-I-REAP) |  |  |  |  | Maragusan | 338000 |  |  | 100% | 338000 | Utilized
Camp Manuel Yan Eco-Tourism & Tribal Park Dev't. (TIEZA) |  |  |  |  | Mawab | 3000000 |  |  | 0% |  | Procurement on process
COMVAL Farm Agri-Eco-Tourism Development (TIEZA) Pasian, Monkayo |  |  |  |  | Pasian, Monkayo | 5000000 |  |  | 0% |  | Procurement on process
Other Special Projects (Provincial Counterpart) | [5 empty] | 2480689 |  |  | 0% |  | Procurement on process
Completion of Health Center Brgy. Magading, Nabunturan |  |  |  |  | Magading, Nabunturan | 220000 |  |  | 0% |  | Declared Savings
Completion of Mp-Bldg. (Madrash) Tunga, Magnaga |  |  |  |  | Magnaga | 160000 |  |  | 64.04% | 102464.5 | 90% On-going
Construction of Drainage at Purok Kauswagan, Purok Bagong, Lipunan, and
Purok Maga Chapoy Brgy. Mapawa, Maragusan |  |  |  |  | Brgy. Mapawa, Maragusan | 628053 |  |  | 0% |  | Procurement on process
Completion of Community Activity Center of Brgy. San Jose, Compostela |  |  |  |  | Brgy. San Jose, Compostela | 300000 |  |  | 0% |  | For change in Nomenclature from completion to const'n.
Rehabilitation of Water System from Purok 1-6, Brgy. Ampawid, Laak |  |  |  |  | Brgy. Ampawid, Laak | 500000 |  |  | 0% |  | POW approved. For 5th Amendatory
Renovation of Multi-Purpose Building in Special Brgy. Libuton, laak |  |  |  |  | Brgy. Libuton, Laak | 500000 |  |  | 0% |  | Procurement on process
Completion of Brgy. Tribal Council Building of Brgy. Cabuyoan, Mabini |  |  |  |  | Brgy. Cabuyoan, Mabini | 500000 |  |  | 0% |  | Cancelled
Construction of Protection Dike & Dessilting of Liboton River at Prk 2A |  |  |  |  | Brgy. Salvacion, Monkayo | 1000000 |  |  | 37.5% | 375000 | Procurement on process
Construction of Hanging Bridge at Purok 4 Brgy. Upper Ulip, Monkayo |  |  |  |  | Brgy. Upper Ulip, Monkayo | 1885193 |  |  | 2.818% | 53116.78 | Procurement on process
Concreting of Brgy. Road Brgy. Bankerohan Sur,Montevista |  |  |  |  | Brgy. Sur Montevista | 1000000 |  |  | 25.1% | 251041.56 | POW approved. For 5th Amendatory
Enhancement of Banana Cardava Consolidation and Marketing, New Bataan |  |  |  |  | New Bataan | 790000 |  |  | 0% |  | Procurement on process
Village Level Rubber Smoke Sheet Processing, Monkayo |  |  |  |  | Monkayo | 838000 |  |  | 0% |  | Procurement on process
W/S Improvement of Sitio Lawaan, Brgy. Kingking, Pantukan (oppap-pamana) |  |  |  |  | Brgy. Kingking, Pantukan | 1050000 |  |  | 0% |  | Procurement on process
Sub - Total | [5 empty] | 74984223.61 |  |  | 2397% | 16917396.08
[7 empty] | DATE STARTED |  | PROJECT STATUS
[8 empty] | TARGET |  | TOTAL
[8 empty] | COMPLETION | % OF | COST INCURRED
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST |  | DATE | COMPLETION | TO DATE
8917 (MOOE)
ECONOMIC DEVELOPMENT:
| Maintenance of roads/bridges - District 1 |  |  |  | Provincewide | 25107500 | 2017-01-03 | 2017-12-29 | 63.31% | 15895955.44 | On-going
| Maintenance of roads/bridges - District 2 |  |  |  | Provincewide | 23677846 | 2017-01-03 | 2017-12-29 | 81.11% | 19204679.22 | On-going
8918 (C.O)
| Construction and Heavy Equipment |  |  |  | Provincewide | 65000000 |  |  | 99.69% | 64800000 | Purchased Heavy Equipment
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
|  | Interest Expenses |  |  |  | 16228749 |  |  | 72.92% | 11834330.44 | Paid to Land Bank of the Phils.
|  | Loans Payable |  |  |  | 62564884 |  |  | 100% | 62564883.25 | Paid to Land Bank of the Phils.
|  |  | Sub - Total |  |  | 192578979 |  |  | 90.51% | 174299848.35
Grand Total | [5 empty] | 267563202.61 |  |  | 71.47% | 191217244.43
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  |  | As to Appropriation/Obligation | [6 empty] | Approved:
|  |  | EVA JEAN S. LICAYAN |  |  |  |  | JAYVEE TYRON L. UY
|  |  | Provincial Budget Officer |  |  |  |  | Governor

## Sheet1 (hidden)
40000000
1080000
905000
1000000
500000
750000
500000
1300000
1300000
1300000
1300000
500000
370000
875000
880000
625000
705000
58000
1000000
710000
1565000
1665000
1870000
1020000
985000
1405000
2260000
1490000
1890000
910000
1000000
645000
755000
810000
795000
1000000
1500000
5000000
1000000
1500000
1000000
1000000
1000000
5000000
2000000
1000000
1500000
700000
2500000
700000
2500000
700000
500000
500000
500000
147933.82
231546.6
149098.67
249273.02
221137.31
98784.86
118685.62
8355000
700000
116094459.9