## SHEET (hidden)
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of March 31, 2019
PROGRAM OR PROJECT |  |  |  | LOCATION |  | DATE STARTED |  | OBLIGATION
[5 empty] | TOTAL COST |  | TARGET | % OF | TOTAL | REMARKS
[5 empty] | Appropriation |  | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[7 empty] | DATE | APPROPRIATION | TO DATE
Annual Budget
SOCIAL DEVELOPMENT:
1918 (C.O)
Construction of Gym, Purok 2, Poblacion, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Construction of Gym, Mangayon NHS, Brgy. Mangayon, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | CONTRACT. for Pre-Procurement Conference.
Concreting of Road going to Valderama ES & NHS, Brgy. Ngan, Compostela |  |  |  | Compostela | 3000000 |  |  | 0% | 0 | Purchase Request on Process
Improvement of Water System, Brgy. Babag, Monkayo |  |  |  | Monkayo | 1200000 |  |  | 0% | 0 | Program of Works for Approval
Construction of Brgy. Stage, Brgy. Kao, Nabunturan |  |  |  | Nabunturan | 850000 |  |  | 0% | 0 | Purchase Request on Process
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  |  | New Bataan | 3000000 |  |  | 0% | 0 | For change in nomenclature from renovation to construction
Rehabilitation of Level II Water System, Brgy. Belmonte, Laak |  |  |  | Laak | 1500000 |  |  | 0% | 0 | For Detailed Engineering Design
Construction of Gym, Brgy. Poblacion, Maco |  |  |  | Maco | 5000000 |  |  | 0% | 0 | CONTRACT. Purchase Request on Process
Construction of Water System, Brgy. Taglawig, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0 | Program of Works on process.
Construction of Gym, Sitio Boringot, Brgy. Napnapan, Pantukan |  |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym, Sitio Panganason, Brgy, Kingking, Pantukan |  |  |  | Pantukan | 3500000 |  |  | 0% | 0 | CONTRACT. For pre-bidding.
Construction of Gym Brgy. Tagdangua, Pantukan |  |  |  | Pantukan | 4000000 |  |  | 0% | 0 | For verification of project location. Waiting for brgy. captain's recommendation
Completion of Multi-purpose Building, Brgy Kingking, Pantukan NHS |  |  |  | Pantukan | 2000000 |  |  | 0% | 0 | Purchase Request on Process
Completion of Multi-purpose Building, Brgy. Kingking CES. Pantukan |  |  |  | Pantukan | 1000000 |  |  | 0% | 0 | Purchase Request on Process
Renovation of Dry Market, Brgy. Poblacion, Monkayo |  |  |  | Monkayo | 3000000 |  |  | 0% | 0
Construction of Brgy. Del Pilar Gym, Brgy. Del Pilar, Mabini |  |  |  | Mabini | 3000000 |  |  | 0% | 0
Development of Eco- Tourism Park Phase 2, Pantukan |  |  |  | Pantukan | 5000000 |  |  | 0%
Construction of Brgy. Stage, Brgy. Nuevo Iloco, Mawab |  |  |  | Mawab | 850000 |  |  | 0% | 0
Purchase of Lot for Happy Village, Brgy. Nueva Visayas, Mawab |  |  |  | Mawab | 2000000 |  |  | 0% | 0
Purchase of lot for the Expansion of Compostela Valley Provincial Hospitals |  |  |  |  | 3000000 |  |  | 0% | 0
Purchase of lot for the Development of Provincial Sports Complex |  |  |  |  | 12000000 |  |  | 0% | 0
Sub - Total Social Development |  |  |  |  | 66400000 |  |  |  | 0
ECONOMIC DEVELOPMENT:
1918 (MOOE)
Provincial Counterpart for Special Projects |  |  |  |  | 26719272.38 |  |  | 0% | 0
8917 (CO)
Rehabilitation Of Provincial Roads/ Bridges - District 1 |  |  |  | Provincewide | 28917741 |  |  | 4.801% | 1388279.87 | 4.80% Accomplished
Rehabilitation Of Provincial Roads/ Bridges - District 2 |  |  |  | Provincewide | 28584329 |  |  | 10.49% | 2999297.21 | 10.49% Accomplished
Rehabilitation of Farm-to-Market Roads (FMRS) - Provincewide |  |  |  | Provincewide | 5000000 |  |  | 0% | 0
Sub - Total Economic Development |  |  |  |  | 89221342.38 |  |  |  | 4387577.08
OTHER SERVICES:
1918 (CO)
Construction of Multi-Purpose Building - Provincewide |  |  |  | Provincewide | 1800000 |  |  | 0% | 0
Rehabilitation of Water System |  |  |  |  | 5000000 |  |  | 0% | 0
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  |  | 18109696.62 |  |  | 67.8% | 12279081.78 | Paid to Land Bank
| Loans Payable |  |  |  | 114338961 |  |  | 42.51% | 48605518.53 | Paid to Land Bank
Sub - Total Other Purposes |  |  |  |  | 139248657.62 |  |  |  | 60884600.31
Total Annual Budget |  |  |  |  | 294870000 |  |  |  | 65272177.39
Supplemental Budget No. 1
1918 (C.O)
Completion of Covered Court - Kinuban, Maco |  |  |  | Maco | 66304.34 |  |  | 0% | 0
Const. of PDEA MP Bldg., PPO-Nabunturan |  |  |  | Nabunturan | 62666.01 |  |  | 0% | 0
Imp. of MP Building- Maragusan |  |  |  | Maragusan | 5000000 |  |  | 0% | 0
Const. of Covered Court - Tagugpo NHS |  |  |  | Pantukan | 1150000 |  |  | 0% | 0
Const. of Public Terminal, Brgy. Camanlangan, New Bataan |  |  |  | New Bataan | 2000000 |  |  | 0% | 0
Completion of Municipal Tribal Hall, Pantukan |  |  |  | Pantukan | 2500000 |  |  | 0% | 0
Imp. of MP Bulding (Women Crisis Center), Brgy. Cabidianan, Nabunturan |  |  |  | Nabunturan | 3000000 |  |  | 0% | 0
Const. of MP Building (Bahay Pag-Asa) |  |  |  |  | 1000000 |  |  | 0% | 0
Const. of Gym, Brgy. Teresa, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0
Const. of PDEA MP Bldg., PPO-Nabunturan- Phase II |  |  |  | Nabunturan | 2500000 |  |  | 0% | 0
Const. of Covered Court - Kidawa, Laak |  |  |  | Laak | 220000 |  |  | 0% | 0
Conc. of Road with Drainage Component, Brgy. Cabidianan, Nabunturan |  |  |  | Nabunturan | 2833114.38 |  |  | 0% | 0
Conc. of Junction Nat'l Highway - Purok 2 to PRC, Brgy. Sta. Maria |  |  |  | Nabunturan | 1486992.37 |  |  | 0% | 0
Const. of Brgy. Stage, Brgy. Nueva Visayas, Mawab |  |  |  | Mawab | 850000 |  |  | 0% | 0
Imp. of Water System-Coronobe, Maragusan |  |  |  | Maragusan | 489400 |  |  | 0% | 0
Const. of WS, Brgy. Del Pilar, Mabini |  |  |  | Mabini | 3000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Tagnocon, Nabunturan |  |  |  | Nabunturan | 3000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Kinuban, Maco |  |  |  | Maco | 5000000 |  |  | 0% | 0
Const. of Potable WS, Brgy. Panibasan, Maco |  |  |  | Maco | 3000000 |  |  | 0% | 0
Imp. of WS-Brgy. Babag, Monkayo |  |  |  | Monkayo | 427500 |  |  | 0% | 0
Const. of Health Center-Mapaang, Maco |  |  |  | Maco | 1500000 |  |  | 0% | 0
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
| Interest Expenses |  |  |  | 3557622.9 |  |  | 0% | 0
Total Supplemental Budget No. 1 |  |  |  |  | 45643600 |  |  |  | 0
Grand Total |  |  |  |  | 340513600 |  |  |  | 65272177.39
Summary: | [7 empty] | %of Obligation/
[5 empty] | Appropriation |  |  | Appropriation | Obligation
| 1918 | Social Development |  |  | 115285977.1 |  |  | 0% | 0
| 8917 | Economic Development |  |  | 89221342.38 |  |  | 4.918% | 4387577.08
| 9911 | Financial Expenses |  |  | 136006280.52 |  |  | 44.77% | 60884600.31
|  | Grand Total |  |  | 340513600 |  |  | 19.17% | 65272177.39
|  |  |  | check | 340513600
0
65272177.39
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  | As to Appropriation/Obligation |  |  | As to Project Status: |  |  |  | Approved:
|  | EVA JEAN S. LICAYAN, ENP, REB, MPA |  | ROMEO B. CELESTE, ENP |  | ENGR. RODERICK M. DIGAMON |  |  | JAYVEE TRON L. UY, MPA
|  | Provincial Budget Officer |  | Provincial Planning & Development Office |  | Provincial Engineer's Office |  |  | Governor
282039226.9
-58474373.1

## PRINT
Republic of the Philippines
Province of Davao De Oro
Provincial Accountant's Office
Ground Floor, Executive Building, Provincial Capitol, Cabidianan, Nabunturan, Davao De Oro | [9 empty] | yellow social
20% COMPONENT OF THE IRA UTILIZATION | [9 empty] | white economic
As of March 31, 2021
green environmental
PROGRAM OR PROJECT |  |  | LOCATION | TOTAL COST APPROPRIATION | DATE STARTED | TARGET COMPLETION DATE | OBLIGATION
[7 empty] | % OF | TOTAL | REMARKS
[7 empty] | OBLIGATION/ | COST INCURRED | (PROJECT STATUS)
[7 empty] | APPROPRIATION | TO DATE
ANNUAL BUDGET
SOCIAL DEVELOPMENT:
1. Concreting Of Road, Purok Lemonsito, Magcagong To |  |  | Maragusan | 5000000
Brgy. Mabugnao, Maragusan
2. Concreting Of Road, Purok Malinawon, Mapawa (JNH) |  |  | Maragusan | 5000000
To New Patung, Mapawa, Maragusan
3. Construction Of 100-meter Road At Brgy. San Roque, Nabunturan |  |  | Nabunturan | 2000000
4. Concreting of Road, Brgy. Mainit, Nabunturan |  |  | Nabunturan | 1500000
5. Construction Of Barangay Health Station, Puting Bato, Brgy. Ngan Compostela |  |  | Compostela | 3000000
6. Construction Of Barangay Health Station, Side 4, Mangayon Compostela |  |  | Compostela | 2500000
7. Construction Of Barangay Health Center, Brgy. Talian, Maragusan |  |  | Maragusan | 3000000
8. Construction Of Bridge With Revetment, Brgy. Bukal, Nabunturan |  |  | Nabunturan | 20000000
9. Construction Of Multi-purpose Bldg. (bleachers |  |  | Maco | 2000000
And Stage), Brgy. New Asturias, Maco
10. Construction Of Multi-purpose Bldg. (day Care |  |  | Pantukan | 1500000
Center), Prk. Binaba, Napnapan, Pantukan
11. Construction Of Multi-purpose Building, Brgy. |  |  | New Bataan | 6500000
Manurigao, New Btaan
12 Construction Of Multipurpose Building (day Care |  |  | Maragusan | 1500000
Center), Brgy. Cambagang, Maragusan
13. Construction Of Multipurpose Building (day Care |  |  | Maco | 1500000 |  |  |  |  | Contract. Pre-procurement process.
Center), Brgy. Magangit, Maco
14. Construction Of Multipurpose Building (day Care |  |  | Maragusan | 1500000
Center), Brgy. New Katipunan, Maragusan
15. Construction Of Multipurpose Building (day Care |  |  | Nabunturan | 1500000
Center), Brgy. Pangutosan, Nabunturan
16. Construction Of Multipurpose Building (day Care |  |  | Mawab | 1500000
E/S, Bawani, Mawab
17 Construction Of Multipurpose Building (day Care |  |  | Compostela | 2000000
Center), Puting Bato, Quarry, Brgy. Ngan, Compostela
18. Construction Of Multipurpose Building (day Care |  |  | Compostela | 1500000
Center), Side 4, Mangayon, Compostela
19. Construction Of Multipurpose Building (gym With |  |  | Maco | 4000000
Stage) Sitio Liboac, Brgy. Elizalde, Maco
20. Construction Of Multipurpose Building |  |  | Laak | 3000000 |  |  |  |  | Contract. Awarded to LLM Unified Builders & Trading Corp.
(gymnasium), Brgy. Macopa, Laak
21. Construction Of Multipurpose Building (social |  |  | Maco | 2500000 |  |  |  |  | Contract. Pre-procurement process. | wala sa project status
Hall) Teresa Nhs-extension, Brgy. Teresa, Maco
22. Construction Of Multipurpose Building (stage With |  |  | Pantukan | 3000000 |  |  |  |  | Contract. Awarded to Lira Construction.
Bleachers), Barangay Bongabong, Pantukan
23. Construction Of Multipurpose Building With Stage |  |  | Pantukan | 6500000
at Boringot Nhs, Brgy. Napnapan, Pantukan
24. Construction Of Multipurpose Building With Stage, Sitio Panganason, Brgy. Kingking, Pantukan |  |  | Pantukan | 6500000
25. Construction Of Multipurpose Building, Poblacion, Mabini |  |  | Mabini | 10000000
26. Construction Of Road At Prk. 2 Relocation Site, Brgy. Fuentes, Pantukan |  |  | Pantukan | 2000000
27. Construction Of Road, Poblacion, Laak |  |  | Laak | 10000000 |  |  |  |  | Contract. Bidded.
28. Improvement & Rehabilitation Of Multipurpose Building, Public Market, Brgy. Poblacion, Nabunturan |  |  | Nabunturan | 10000000
29. Improvement Of Multipurpose Building (bleachers |  |  | Laak | 2000000 |  |  |  |  | Contract. Awarded to LLM Unified Builders & Trading Corp.
And Stage) Brgy. Sto. Niño, Laak
30. Improvement Of Multipurpose Building (day Care |  |  | Monkayo | 500000
Center), Brgy. San Isidro, Monkayo
31. Improvement Of Multipurpose Building (gym With |  |  | Mawab | 500000
Bleachers), Brgy. Concepcion, Mawab
32. Improvement Of Multipurpose Building (Social Hall), Sitio Diat, Brgy. Napnapan, Pantukan |  |  | Pantukan | 1000000
33. Improvement Of Multipurpose Building (stage), |  |  | Mawab | 1000000 |  |  |  |  | Contract. For bidding.
Brgy. Tuburan, Mawab
34. Provincial Counterpart To Special Projects |  |  |  | 18919883.25
35. Purchase Of Lot For Davao De Oro Medical Center |  |  |  | 8000000
36. Rehabilitation Of Barangay Health Center, Brgy. Antequera, Nabunturan |  |  | Nabunturan | 500000
Sub - Total Social Development |  |  |  | 152919883.25 |  |  |  | 0
ECONOMIC DEVELOPMENT:
37. Rehabilitation of Provincial Roads/ Bridges - District 1 |  |  | Provincewide | 29497000 |  |  | 15.88% | 4682736.76 | On going
38. Rehabilitation of Provincial Roads/ Bridges - District 2 |  |  | Provincewide | 29157000 |  |  | 10.44% | 3043510.78 | On going
39. Loans Payable - Domestic |  |  |  | 87723076.92 |  |  | 39.92% | 35015384.61
40. Interest Expenses |  |  |  | 10203039.83 |  |  | 48.65% | 4963302.74
41. Construction Of Terminal And Public Market Complex, Sitio Mendoza, Brgy. Kingking, Pantukan (Phase 3) |  |  | Pantukan | 20000000
Sub - Total Economic Development |  |  |  | 176580116.75 |  |  |  | 47704934.89
ENVIRONMENTAL MANAGEMENT:
42. Construction Of Animal Quarantine Control & Revenue |  |  | Monkayo, | 20000000
Generation Center (Monkayo, Mawab and Maco Borders) |  |  | Mawab, Maco
43. Construction Of Water System At Camp 4, Brgy. |  |  | Pantukan | 3000000
Pindasan, Pantukan
44. Construction Of Water System, Brgy. Coronobe, Maragusan |  |  | Maragusan | 3000000
45. Improvement Of Water System, Brgy. Bagong Silang, |  |  | Maragusan | 3000000
Maragusan
46. Improvement Of Water System, Brgy. Cabidianan, |  |  | Nabunturan | 500000
Nabunturan
47. Improvement Of Water System, Cabidianan E/s, |  |  | Nabunturan | 300000
Brgy. Cabidianan
48. Improvement Of Water System, Cabidianan Nhs |  |  | Nabunturan | 700000
Brgy. Cabidianan
Sub - Total Environmental Management |  |  |  | 30500000 |  |  |  | 0
TOTAL ANNUAL BUDGET |  |  |  | 360000000 |  |  |  | 47704934.89
Summary: | [6 empty] | % of Obligation/ |  |  | 260213244.01 | #REF! | zero means no changes to obligations
|  |  |  | Appropriation |  |  | Appropriation | Obligation
|  | Social Development |  | 152919883.25 |  |  | 0% | 0
|  | Economic Development |  | 176580116.75 |  |  | 27.02% | 47704934.89
|  | Environmental Management |  | 30500000 |  |  | 0% | 0
|  | Grand total |  | 360000000 |  |  | 13.25% | 47704934.89
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
|  | as to Appropriation/Obligation: |  |  | as to Project Status: |  |  |  | Approved:
|  | (Sgd.) | (Sgd.) |  | (Sgd.) |  |  | (Sgd.) | (Sgd.)
EVA JEAN S. LICAYAN, ENP ARIEL D. MANDAWE, CPA RAYMUNDO J. PAJARITO ENGR. RODERICK M. DIGAMON JAYVEE TYRON L. UY, MPA
Provincial Budget Officer OIC-Provincial Accountant OIC-Provincial Planning & Provincial Engineer Governor
Development Officer
|  |  |  | 367266214.71 |  |  |  | 146370185.99
|  |  |  | 7266214.71 |  |  |  | 98665251.1

## roads and bridges (hidden)
d1 |  | d2
1406312.94 | 1 | 450666.82
346641.07 | 2 | 3691173.19
329338.25 | 3 | 1187823.25
860736.66 | 4 | 302357.89
754121.02 | 5 | 443858.29
665957.25 | 6 | 374428.06
544873.39 | 7 | 639808.52
1353782.24 | 8 | 1222449.7
1587558.73 | 9 | 961270.42
1551379.51 | 10 | 502575.03
1069370.6 | 11 | 358411.19
607875.22 | 12 | 375094.6
721191.34 | 13 | 146437.95
963298.57 | 14 | 236740.16
2760936.08 | 15 | 291795.83
1286500.07 | 16 | 1874149.59
870815.18 | 17 | 596713.11
418001.17 | 18 | 375020.62
1505817.84 | 19 | 394342.91
1238228.44 | 20 | 601211.95
359101.69 | 21 | 370613.91
256470.21 | 22 | 450447.22
1002796.15 | 23 | 33831.18
738974.46 | 24 | 560682.9
1238663.92 | 25 | 287876.96
245287.26 | 26 | 190649.67
287922.45 | 27 | 374932.65
649684.57 | 28 | 300551.75
576306.14 | 29 | 252591.74
454766.29 | 30 | 245486.18
291166.54 | 31 | 174550.8
656730.56 | 32 | 495228.2
262775.76 | 33 | 117163.28
| 34 | 299344.62
27863381.57 | 35 | 374976.44
| 36 | 104511.58
| 37 | 375108.65
| 38 | 1493740.5
| 39 | 97714.15
| 40 | 296397.92
| 41 | 1109651.47
| 42 | 370132.58
| 43 | 600755.37
| 44 | 798288.05
| 45 | 1130549.9
| 46 | 427997.11
| 47 | 900692.95
| 48 | 749249.09
28010045.9

## July-Sept. (hidden)
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST | DATE STARTED |  | OBLIGATION
[8 empty] | TARGET | % OF | TOTAL | REMARKS
[8 empty] | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[8 empty] | DATE | APPROPRIATION | TO DATE
1918 (MOOE)
SOCIAL DEVELOPMENT:
F/A Repair/Rehabilitation of Farm-to-Market Roads (FMR) |  |  |  |  | Provincewide | 5000000 |  |  | 0% |  | Program of works on process
F/A Provincial Counterpart for Special Programs/Projects |  |  |  |  | Provincewide | 10000000 |  |  | 0% |  | Program of works on process
F/A Repair/Rehabilitation of Water System |  |  |  |  | Provincewide | 4000000 |  |  | 0% |  | Program of works on process
Purchase of Various Sizes of HDPE Pipes
Distribution of Materials for Brgys. Magnaga, Bongbong, Matiao, Tambongon of Pantukan and Brgy. Pangi of Maco
F/A Construction/Purchase of Post Harvest Facilities |  |  |  |  | Provincewide | 1000000 |  |  | 0% |  | Procurement on process
F/A Completion of Multi-Purpose Building-Barangay Lahi, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Concreting of Barangay Road-Barangay Magcagong, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Acquisition of Dump Truck-Barangay New Manay, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Purok Multi-Purpose Center |  |  |  |  | Brgy. New Panay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Water System |  |  |  |  | Brgy. Talian, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. Mapawa, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. New Albay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Covered Court |  |  |  |  | Brgy. Mauswagon, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Multi-Purpose Building |  |  |  |  | Brgy. Coronobe, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Covered Court |  |  |  |  | Prk 1 Brgy. Paloc, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Purchase of Dump Truck |  |  |  |  | Laak | 2400000 |  |  | 0% |  | Procurement on process
F/A Construction of Covered Court |  |  |  |  | Brgy. Ceboleda, Laak | 1000000 |  |  | 76.27% | 762650.5 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Banbanon, Laak | 1000000 |  |  | 72.93% | 729340.48 | 20% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Bagong Silang, Laak | 1500000 |  |  | 71.54% | 1073131.28 | 15% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. New Bethlehem, Laak | 1000000 |  |  | 69.58% | 695782.73 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Kiokmay, Laak | 1000000 |  |  | 65.71% | 657073.29 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Cabuyuan, Mabini | 1000000 |  |  | 72.51% | 725068.58 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Salvacion, Mawab | 1000000 | 2017-06-27 | 2017-09-25 | 94.32% | 943242.52 | 30% 0n-going
Construction of Day Care Center- Sitio Cambodlot, San Miguel, Compostela |  |  |  |  | Compostela | 245446.21 | 2017-05-30 | 2017-08-18 | 90.62% | 222432.28 | 98% Temporarily Suspended.
Concreting of Road @ Bonifacio-Garcia St. Brgy. Poblacion, Compostela |  |  |  |  | Brgy. Compostela | 237240.2 | 2017-04-10 | 2017-05-05 | 95.16% | 225760.96 | Completed
Concreting of Road @ Emilio Aguinaldo St. Purok 1 |  |  |  |  | Brgy. Poblacion, Compostela | 206207.36 | 2017-05-02 | 2017-06-21 | 98.04% | 202175.97 | Completed
Concreting of Road from Brgy. Dauman to Brgy. Concepcion, Montevista |  |  |  |  | Brgy. Concepcion, Montevista | 1064369.3 | 2017-04-17 | 2017-08-25 | 96.26% | 1024555 | Completed
Concreting of Road Brgy. San Vicente, Montevista |  |  |  |  | Brgy. San Vicente, Montevista | 223652.46 | 2017-04-20 | 2017-06-20 | 97.43% | 217906.77 | Completed
Construction of Covered Court-Brgy. Cabacungan, Nabunturan |  |  |  |  | Brgy. Cabacungan, Nabunturan | 322320.39 | 2017-04-12 | 2017-07-27 | 57.83% | 186400.24 | Completed
Construction of Covered Court-Brgy. Basak (stage), Nabunturan |  |  |  |  | Nabunturan | 92762.56 | 2017-04-11 | 2017-05-24 | 99.2% | 92016.32 | Completed
F/A-Construction of Covered Court-Brgy. Mt. Diwata, Monkayo |  |  |  |  | Monkayo | 1000000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
Concreting of FMR, Purok 5, Tagaytay, Brgy. Mipangi, Nabunturan |  |  |  |  | Nabunturan | 267931.28 | 2017-05-02 | 2017-05-17 | 99.98% | 267886.12 | Completed
Concreting of Road from Junction National Highway to Purok 6 |  |  |  |  | Nabunturan | 1222342.98 | 2017-04-17 | 2017-08-15 | 55.44% | 677619.83 | 95% On-going
Concreting of Road at Brgy. Cabacungan, Nabunturan |  |  |  |  | Nabunturan | 576798.44 | 2017-04-12 | 2017-06-22 | 73.13% | 421799 | Completed
Concreting of Road from Junction Nat'l. H-way to Cabidianan Annex HS |  |  |  |  | Brgy. Nabunturan | 329035.58 | 2017-04-17 | 2017-07-05 | 95.32% | 313648.82 | Completed
Concreting of Road at Mapaang Section |  |  |  |  | Brgy. Mapaang, Maco | 212862.75 | 2017-05-16 | 2017-05-25 | 40.08% | 85316.88 | Completed
Construction of Multi-Purpose Building |  |  |  |  | Brgy. Poblacion, Mawab | 81822.86 | 2017-05-03 | 2017-06-07 | 71.44% | 58454.82 | 98% Temporarily Suspended.
Construction of Multi-Purpose Building (Council of Women) |  |  |  |  | Brgy. Las Arenas, Pantukan | 200030.48 | 2017-04-17 | 2017-06-20 | 63.25% | 126526.2 | 85% On-going
Construction of Tribal Hall |  |  |  |  | Brgy. Poblacion, Pantukan | 546787 | 2017-06-13 | 2017-10-06 | 35.96% | 196650.73 | 20% On-going
Construction of Multi-Purpose Building (Madrasah) |  |  |  |  | Tunga, Monkayo | 226099.1 | 2017-05-08 | 2017-07-18 | 55.51% | 125496.38 | 95% On-going
Construction of Multi-Purpose Building (ABC) |  |  |  |  | Compostela | 137322.6 | 2017-04-17 | 2017-06-15 | 98.16% | 134802.5 | Completed
Concreting of Road from Junction National H-way to Brgy. Hall |  |  |  |  | Bankerohan Sur, Montevista | 77881.34 | 2017-05-29 | 2017-06-13 | 94.37% | 73496.66 | Completed
Concreting of Road from Prk 8-Prk 7 to Junction National |  |  |  |  | Montevista | 420064.72 | 2017-04-17 | 2017-07-31 | 97.26% | 408538.38 | Completed
F/A Construction of Hanging Bridge (footbridge) Prk 9 |  |  |  |  | Salvacion, Monkayo | 650000 |  |  | 100% | 650000 | For Fund Transfer to Municipality (FTM)
F/A Construction of Slaughter House, Pantukan |  |  |  |  | Pantukan | 4700000 |  |  | 95.74% | 4500000 | For Fund Transfer to Municipality (FTM)
1918 (C.O)
Rehab. Of Brgy. Poblacion-Brgy. Naboc FMR, Monkayo (PRDP-BUILD) |  |  |  |  | Monkayo | 1358700 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Monkayo | 565505 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Maparat, Compostela | 521906 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Libasan, Nabunturan | 521902 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Linda, Nabunturan | 542264 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Kilagding, Laak | 543034 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Elizalde, Maco (OPPAP-PAMANA) |  |  |  |  | Brgy. Elizalde, Maco | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Camanlangan, New Bataan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Bataan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Bongbong, Pantukan (OPPAP-PAMANA) |  |  |  |  | Brgy. Bongbong, Pantukan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Monkayo (OPPAP-PAMANA) |  |  |  |  | Brgy. Poblacion, Monkayo | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Laak (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Laak | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Mabini (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Mabini | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. New Panay, Maragusan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Panay, Maragusan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Ngan, Compostela (OPPAP-PAMANA) |  |  |  |  | Brgy. Ngan, Compostela | 350000 |  |  | 0% |  | Procurement on process
Tablea Processing & Marketing Enterprise (PRDP-I-REAP) |  |  |  |  | Maragusan | 338000 |  |  | 100% | 338000 | Utilized
Camp Manuel Yan Eco-Tourism & Tribal Park Dev't. (TIEZA) |  |  |  |  | Mawab | 3000000 |  |  | 0% |  | Procurement on process
COMVAL Farm Agri-Eco-Tourism Development (TIEZA) Pasian, Monkayo |  |  |  |  | Pasian, Monkayo | 5000000 |  |  | 0% |  | Procurement on process
Other Special Projects (Provincial Counterpart) | [5 empty] | 2480689 |  |  | 0% |  | Procurement on process
Completion of Health Center Brgy. Magading, Nabunturan |  |  |  |  | Magading, Nabunturan | 220000 |  |  | 0% |  | Declared Savings
Completion of Mp-Bldg. (Madrash) Tunga, Magnaga |  |  |  |  | Magnaga | 160000 |  |  | 64.04% | 102464.5 | 90% On-going
Construction of Drainage at Purok Kauswagan, Purok Bagong, Lipunan, and
Purok Maga Chapoy Brgy. Mapawa, Maragusan |  |  |  |  | Brgy. Mapawa, Maragusan | 628053 |  |  | 0% |  | Procurement on process
Completion of Community Activity Center of Brgy. San Jose, Compostela |  |  |  |  | Brgy. San Jose, Compostela | 300000 |  |  | 0% |  | For change in Nomenclature from completion to const'n.
Rehabilitation of Water System from Purok 1-6, Brgy. Ampawid, Laak |  |  |  |  | Brgy. Ampawid, Laak | 500000 |  |  | 0% |  | POW approved. For 5th Amendatory
Renovation of Multi-Purpose Building in Special Brgy. Libuton, laak |  |  |  |  | Brgy. Libuton, Laak | 500000 |  |  | 0% |  | Procurement on process
Completion of Brgy. Tribal Council Building of Brgy. Cabuyoan, Mabini |  |  |  |  | Brgy. Cabuyoan, Mabini | 500000 |  |  | 0% |  | Cancelled
Construction of Protection Dike & Dessilting of Liboton River at Prk 2A |  |  |  |  | Brgy. Salvacion, Monkayo | 1000000 |  |  | 37.5% | 375000 | Procurement on process
Construction of Hanging Bridge at Purok 4 Brgy. Upper Ulip, Monkayo |  |  |  |  | Brgy. Upper Ulip, Monkayo | 1885193 |  |  | 2.818% | 53116.78 | Procurement on process
Concreting of Brgy. Road Brgy. Bankerohan Sur,Montevista |  |  |  |  | Brgy. Sur Montevista | 1000000 |  |  | 25.1% | 251041.56 | POW approved. For 5th Amendatory
Enhancement of Banana Cardava Consolidation and Marketing, New Bataan |  |  |  |  | New Bataan | 790000 |  |  | 0% |  | Procurement on process
Village Level Rubber Smoke Sheet Processing, Monkayo |  |  |  |  | Monkayo | 838000 |  |  | 0% |  | Procurement on process
W/S Improvement of Sitio Lawaan, Brgy. Kingking, Pantukan (oppap-pamana) |  |  |  |  | Brgy. Kingking, Pantukan | 1050000 |  |  | 0% |  | Procurement on process
Sub - Total | [5 empty] | 74984223.61 |  |  | 2397% | 16917396.08
[7 empty] | DATE STARTED |  | PROJECT STATUS
[8 empty] | TARGET |  | TOTAL
[8 empty] | COMPLETION | % OF | COST INCURRED
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST |  | DATE | COMPLETION | TO DATE
8917 (MOOE)
ECONOMIC DEVELOPMENT:
| Maintenance of roads/bridges - District 1 |  |  |  | Provincewide | 25107500 | 2017-01-03 | 2017-12-29 | 63.31% | 15895955.44 | On-going
| Maintenance of roads/bridges - District 2 |  |  |  | Provincewide | 23677846 | 2017-01-03 | 2017-12-29 | 81.11% | 19204679.22 | On-going
8918 (C.O)
| Construction and Heavy Equipment |  |  |  | Provincewide | 65000000 |  |  | 99.69% | 64800000 | Purchased Heavy Equipment
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
|  | Interest Expenses |  |  |  | 16228749 |  |  | 72.92% | 11834330.44 | Paid to Land Bank of the Phils.
|  | Loans Payable |  |  |  | 62564884 |  |  | 100% | 62564883.25 | Paid to Land Bank of the Phils.
|  |  | Sub - Total |  |  | 192578979 |  |  | 90.51% | 174299848.35
Grand Total | [5 empty] | 267563202.61 |  |  | 71.47% | 191217244.43
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  |  | As to Appropriation/Obligation | [6 empty] | Approved:
|  |  | EVA JEAN S. LICAYAN |  |  |  |  | JAYVEE TYRON L. UY
|  |  | Provincial Budget Officer |  |  |  |  | Governor

## Sheet1 (hidden)
40000000
1080000
905000
1000000
500000
750000
500000
1300000
1300000
1300000
1300000
500000
370000
875000
880000
625000
705000
58000
1000000
710000
1565000
1665000
1870000
1020000
985000
1405000
2260000
1490000
1890000
910000
1000000
645000
755000
810000
795000
1000000
1500000
5000000
1000000
1500000
1000000
1000000
1000000
5000000
2000000
1000000
1500000
700000
2500000
700000
2500000
700000
500000
500000
500000
147933.82
231546.6
149098.67
249273.02
221137.31
98784.86
118685.62
8355000
700000
116094459.9