## July-Sept.
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST | DATE STARTED |  | OBLIGATION
[8 empty] | TARGET | % OF | TOTAL | REMARKS
[8 empty] | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[8 empty] | DATE | APPROPRIATION | TO DATE
1918 (MOOE)
SOCIAL DEVELOPMENT:
F/A Repair/Rehabilitation of Farm-to-Market Roads (FMR) |  |  |  |  | Provincewide | 5000000 |  |  | 0% |  | Program of works on process
F/A Provincial Counterpart for Special Programs/Projects |  |  |  |  | Provincewide | 10000000 |  |  | 0% |  | Program of works on process
F/A Repair/Rehabilitation of Water System |  |  |  |  | Provincewide | 4000000 |  |  | 0% |  | Program of works on process
Purchase of Various Sizes of HDPE Pipes
Distribution of Materials for Brgys. Magnaga, Bongbong, Matiao, Tambongon of Pantukan and Brgy. Pangi of Maco
F/A Construction/Purchase of Post Harvest Facilities |  |  |  |  | Provincewide | 1000000 |  |  | 0% |  | Procurement on process
F/A Completion of Multi-Purpose Building-Barangay Lahi, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Concreting of Barangay Road-Barangay Magcagong, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Acquisition of Dump Truck-Barangay New Manay, Maragusan |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Purok Multi-Purpose Center |  |  |  |  | Brgy. New Panay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Water System |  |  |  |  | Brgy. Talian, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. Mapawa, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Multi-Purpose Building |  |  |  |  | Brgy. New Albay, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Improvement of Covered Court |  |  |  |  | Brgy. Mauswagon, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Completion of Multi-Purpose Building |  |  |  |  | Brgy. Coronobe, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Construction of Covered Court |  |  |  |  | Prk 1 Brgy. Paloc, Maragusan | 500000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
F/A Purchase of Dump Truck |  |  |  |  | Laak | 2400000 |  |  | 0% |  | Procurement on process
F/A Construction of Covered Court |  |  |  |  | Brgy. Ceboleda, Laak | 1000000 |  |  | 76.27% | 762650.5 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Banbanon, Laak | 1000000 |  |  | 72.93% | 729340.48 | 20% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Bagong Silang, Laak | 1500000 |  |  | 71.54% | 1073131.28 | 15% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. New Bethlehem, Laak | 1000000 |  |  | 69.58% | 695782.73 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Kiokmay, Laak | 1000000 |  |  | 65.71% | 657073.29 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Cabuyuan, Mabini | 1000000 |  |  | 72.51% | 725068.58 | 5% On-going
F/A Construction of Covered Court |  |  |  |  | Brgy. Salvacion, Mawab | 1000000 | 2017-06-27 | 2017-09-25 | 94.32% | 943242.52 | 30% 0n-going
Construction of Day Care Center- Sitio Cambodlot, San Miguel, Compostela |  |  |  |  | Compostela | 245446.21 | 2017-05-30 | 2017-08-18 | 90.62% | 222432.28 | 98% Temporarily Suspended.
Concreting of Road @ Bonifacio-Garcia St. Brgy. Poblacion, Compostela |  |  |  |  | Brgy. Compostela | 237240.2 | 2017-04-10 | 2017-05-05 | 95.16% | 225760.96 | Completed
Concreting of Road @ Emilio Aguinaldo St. Purok 1 |  |  |  |  | Brgy. Poblacion, Compostela | 206207.36 | 2017-05-02 | 2017-06-21 | 98.04% | 202175.97 | Completed
Concreting of Road from Brgy. Dauman to Brgy. Concepcion, Montevista |  |  |  |  | Brgy. Concepcion, Montevista | 1064369.3 | 2017-04-17 | 2017-08-25 | 96.26% | 1024555 | Completed
Concreting of Road Brgy. San Vicente, Montevista |  |  |  |  | Brgy. San Vicente, Montevista | 223652.46 | 2017-04-20 | 2017-06-20 | 97.43% | 217906.77 | Completed
Construction of Covered Court-Brgy. Cabacungan, Nabunturan |  |  |  |  | Brgy. Cabacungan, Nabunturan | 322320.39 | 2017-04-12 | 2017-07-27 | 57.83% | 186400.24 | Completed
Construction of Covered Court-Brgy. Basak (stage), Nabunturan |  |  |  |  | Nabunturan | 92762.56 | 2017-04-11 | 2017-05-24 | 99.2% | 92016.32 | Completed
F/A-Construction of Covered Court-Brgy. Mt. Diwata, Monkayo |  |  |  |  | Monkayo | 1000000 |  |  | 0% |  | For Fund Transfer to Municipality (FTM)
Concreting of FMR, Purok 5, Tagaytay, Brgy. Mipangi, Nabunturan |  |  |  |  | Nabunturan | 267931.28 | 2017-05-02 | 2017-05-17 | 99.98% | 267886.12 | Completed
Concreting of Road from Junction National Highway to Purok 6 |  |  |  |  | Nabunturan | 1222342.98 | 2017-04-17 | 2017-08-15 | 55.44% | 677619.83 | 95% On-going
Concreting of Road at Brgy. Cabacungan, Nabunturan |  |  |  |  | Nabunturan | 576798.44 | 2017-04-12 | 2017-06-22 | 73.13% | 421799 | Completed
Concreting of Road from Junction Nat'l. H-way to Cabidianan Annex HS |  |  |  |  | Brgy. Nabunturan | 329035.58 | 2017-04-17 | 2017-07-05 | 95.32% | 313648.82 | Completed
Concreting of Road at Mapaang Section |  |  |  |  | Brgy. Mapaang, Maco | 212862.75 | 2017-05-16 | 2017-05-25 | 40.08% | 85316.88 | Completed
Construction of Multi-Purpose Building |  |  |  |  | Brgy. Poblacion, Mawab | 81822.86 | 2017-05-03 | 2017-06-07 | 71.44% | 58454.82 | 98% Temporarily Suspended.
Construction of Multi-Purpose Building (Council of Women) |  |  |  |  | Brgy. Las Arenas, Pantukan | 200030.48 | 2017-04-17 | 2017-06-20 | 63.25% | 126526.2 | 85% On-going
Construction of Tribal Hall |  |  |  |  | Brgy. Poblacion, Pantukan | 546787 | 2017-06-13 | 2017-10-06 | 35.96% | 196650.73 | 20% On-going
Construction of Multi-Purpose Building (Madrasah) |  |  |  |  | Tunga, Monkayo | 226099.1 | 2017-05-08 | 2017-07-18 | 55.51% | 125496.38 | 95% On-going
Construction of Multi-Purpose Building (ABC) |  |  |  |  | Compostela | 137322.6 | 2017-04-17 | 2017-06-15 | 98.16% | 134802.5 | Completed
Concreting of Road from Junction National H-way to Brgy. Hall |  |  |  |  | Bankerohan Sur, Montevista | 77881.34 | 2017-05-29 | 2017-06-13 | 94.37% | 73496.66 | Completed
Concreting of Road from Prk 8-Prk 7 to Junction National |  |  |  |  | Montevista | 420064.72 | 2017-04-17 | 2017-07-31 | 97.26% | 408538.38 | Completed
F/A Construction of Hanging Bridge (footbridge) Prk 9 |  |  |  |  | Salvacion, Monkayo | 650000 |  |  | 100% | 650000 | For Fund Transfer to Municipality (FTM)
F/A Construction of Slaughter House, Pantukan |  |  |  |  | Pantukan | 4700000 |  |  | 95.74% | 4500000 | For Fund Transfer to Municipality (FTM)
1918 (C.O)
Rehab. Of Brgy. Poblacion-Brgy. Naboc FMR, Monkayo (PRDP-BUILD) |  |  |  |  | Monkayo | 1358700 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Monkayo | 565505 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Maparat, Compostela | 521906 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Libasan, Nabunturan | 521902 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Linda, Nabunturan | 542264 |  |  | 0% |  | Procurement on process
Const. of five (5) units Warehouse with solar dryer (PRDP-OTHER-INFRA) |  |  |  |  | Brgy. Kilagding, Laak | 543034 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Elizalde, Maco (OPPAP-PAMANA) |  |  |  |  | Brgy. Elizalde, Maco | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Camanlangan, New Bataan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Bataan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Bongbong, Pantukan (OPPAP-PAMANA) |  |  |  |  | Brgy. Bongbong, Pantukan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Monkayo (OPPAP-PAMANA) |  |  |  |  | Brgy. Poblacion, Monkayo | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Laak (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Laak | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Poblacion, Mabini (OPPAP-PAMANA) |  |  |  |  | Brgy. Pob. Mabini | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. New Panay, Maragusan (OPPAP-PAMANA) |  |  |  |  | Brgy. New Panay, Maragusan | 350000 |  |  | 0% |  | Procurement on process
Const. of Tribal Hall, Brgy. Ngan, Compostela (OPPAP-PAMANA) |  |  |  |  | Brgy. Ngan, Compostela | 350000 |  |  | 0% |  | Procurement on process
Tablea Processing & Marketing Enterprise (PRDP-I-REAP) |  |  |  |  | Maragusan | 338000 |  |  | 100% | 338000 | Utilized
Camp Manuel Yan Eco-Tourism & Tribal Park Dev't. (TIEZA) |  |  |  |  | Mawab | 3000000 |  |  | 0% |  | Procurement on process
COMVAL Farm Agri-Eco-Tourism Development (TIEZA) Pasian, Monkayo |  |  |  |  | Pasian, Monkayo | 5000000 |  |  | 0% |  | Procurement on process
Other Special Projects (Provincial Counterpart) | [5 empty] | 2480689 |  |  | 0% |  | Procurement on process
Completion of Health Center Brgy. Magading, Nabunturan |  |  |  |  | Magading, Nabunturan | 220000 |  |  | 0% |  | Declared Savings
Completion of Mp-Bldg. (Madrash) Tunga, Magnaga |  |  |  |  | Magnaga | 160000 |  |  | 64.04% | 102464.5 | 90% On-going
Construction of Drainage at Purok Kauswagan, Purok Bagong, Lipunan, and
Purok Maga Chapoy Brgy. Mapawa, Maragusan |  |  |  |  | Brgy. Mapawa, Maragusan | 628053 |  |  | 0% |  | Procurement on process
Completion of Community Activity Center of Brgy. San Jose, Compostela |  |  |  |  | Brgy. San Jose, Compostela | 300000 |  |  | 0% |  | For change in Nomenclature from completion to const'n.
Rehabilitation of Water System from Purok 1-6, Brgy. Ampawid, Laak |  |  |  |  | Brgy. Ampawid, Laak | 500000 |  |  | 0% |  | POW approved. For 5th Amendatory
Renovation of Multi-Purpose Building in Special Brgy. Libuton, laak |  |  |  |  | Brgy. Libuton, Laak | 500000 |  |  | 0% |  | Procurement on process
Completion of Brgy. Tribal Council Building of Brgy. Cabuyoan, Mabini |  |  |  |  | Brgy. Cabuyoan, Mabini | 500000 |  |  | 0% |  | Cancelled
Construction of Protection Dike & Dessilting of Liboton River at Prk 2A |  |  |  |  | Brgy. Salvacion, Monkayo | 1000000 |  |  | 37.5% | 375000 | Procurement on process
Construction of Hanging Bridge at Purok 4 Brgy. Upper Ulip, Monkayo |  |  |  |  | Brgy. Upper Ulip, Monkayo | 1885193 |  |  | 2.818% | 53116.78 | Procurement on process
Concreting of Brgy. Road Brgy. Bankerohan Sur,Montevista |  |  |  |  | Brgy. Sur Montevista | 1000000 |  |  | 25.1% | 251041.56 | POW approved. For 5th Amendatory
Enhancement of Banana Cardava Consolidation and Marketing, New Bataan |  |  |  |  | New Bataan | 790000 |  |  | 0% |  | Procurement on process
Village Level Rubber Smoke Sheet Processing, Monkayo |  |  |  |  | Monkayo | 838000 |  |  | 0% |  | Procurement on process
W/S Improvement of Sitio Lawaan, Brgy. Kingking, Pantukan (oppap-pamana) |  |  |  |  | Brgy. Kingking, Pantukan | 1050000 |  |  | 0% |  | Procurement on process
Sub - Total | [5 empty] | 74984223.61 |  |  | 2397% | 16917396.08
[7 empty] | DATE STARTED |  | PROJECT STATUS
[8 empty] | TARGET |  | TOTAL
[8 empty] | COMPLETION | % OF | COST INCURRED
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST |  | DATE | COMPLETION | TO DATE
8917 (MOOE)
ECONOMIC DEVELOPMENT:
| Maintenance of roads/bridges - District 1 |  |  |  | Provincewide | 25107500 | 2017-01-03 | 2017-12-29 | 63.31% | 15895955.44 | On-going
| Maintenance of roads/bridges - District 2 |  |  |  | Provincewide | 23677846 | 2017-01-03 | 2017-12-29 | 81.11% | 19204679.22 | On-going
8918 (C.O)
| Construction and Heavy Equipment |  |  |  | Provincewide | 65000000 |  |  | 99.69% | 64800000 | Purchased Heavy Equipment
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
|  | Interest Expenses |  |  |  | 16228749 |  |  | 72.92% | 11834330.44 | Paid to Land Bank of the Phils.
|  | Loans Payable |  |  |  | 62564884 |  |  | 100% | 62564883.25 | Paid to Land Bank of the Phils.
|  |  | Sub - Total |  |  | 192578979 |  |  | 90.51% | 174299848.35
Grand Total | [5 empty] | 267563202.61 |  |  | 71.47% | 191217244.43
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of Sept. 30, 2017
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  |  | As to Appropriation/Obligation | [6 empty] | Approved:
|  |  | EVA JEAN S. LICAYAN |  |  |  |  | JAYVEE TYRON L. UY
|  |  | Provincial Budget Officer |  |  |  |  | Governor

## July-Sept
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of September 30, 2018
PROGRAM OR PROJECT |  |  |  |  | LOCATION |  | DATE STARTED |  | OBLIGATION
[6 empty] | TOTAL COST |  | TARGET | % OF | TOTAL | REMARKS
[6 empty] | Appropriation |  | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[8 empty] | DATE | APPROPRIATION | TO DATE
1918 (MOOE)
SOCIAL DEVELOPMENT:
Provincial Counterpart for Special Projects | [5 empty] | 40000000 |  |  | 0.73% | 292000 | On-going
Completion of Covered Court-San Isidro |  |  |  |  | Monkayo | 1080000 |  |  | 0.8641% | 9332.27 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Inambatan |  |  |  |  | Monkayo | 905000 |  |  | 1.027% | 9298.29 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Haguimitan |  |  |  |  | Monkayo | 1000000 |  |  | 2.512% | 25115.92 | Contract Bidded last Sept 12, 2018
Completion of Multi-Purpose Hall-Casoon |  |  |  |  | Monkayo | 500000 |  |  | 0% |  | For Change in Nomenclature
Completion of Covered Court-Mayaon |  |  |  |  | Montevista | 750000 |  |  | 70.2% | 526492.33 | For abandonement. Implemented by DPWH
Completion of Covered Court-Cabinuangan Elem. School |  |  |  |  | New Bataan | 500000 |  |  | 59.82% | 299099.63 | On-going
Completion of Covered Court-Pamintaran |  |  |  |  | Maragusan | 1300000 |  |  | 0% |  | Fund transfer to Municipality (FTM)
Completion of Covered Court-New Albay, Maragusan |  |  |  |  | Maragusan | 1300000 |  |  | 0% |  | Fund transfer to Municipality (FTM)
Completion of Covered Court-Talian, Maragusan |  |  |  |  | Maragusan | 1300000 |  |  | 0% |  | Fund transfer to Municipality (FTM)
Completion of Covered Court-Tigbao, Maragusan |  |  |  |  | Maragusan | 1300000 |  |  | 0% |  | Fund transfer to Municipality (FTM)
Completion of Multi-Purpose Building-Cambagang |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | Fund transfer to Municipality (FTM)
Completion of Covered Court-Cadunan, Mabini |  |  |  |  | Mabini | 370000 |  |  | 82.8% | 306344.52 | Completed on July 31, 2018
Completion of Covered Court-Saosao |  |  |  |  | Mawab | 875000 |  |  | 0.5714% | 5000 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Tuburan |  |  |  |  | Mawab | 880000 |  |  | 0.5682% | 5000 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Concepcion |  |  |  |  | Mawab | 625000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Covered Court-Salvacion |  |  |  |  | Mawab | 705000 |  |  | 1.305% | 9201.39 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Libasan |  |  |  |  | Nabunturan | 58000 |  |  | 76.01% | 44085.72 | Completed on Sept 28, 2018
Completion of Covered Court-Ogao |  |  |  |  | Nabunturan | 1000000 |  |  | 78.4% | 783973.69 | Completed on Sept 28, 2018
Completion of Covered Court-Anislagan |  |  |  |  | Nabunturan | 710000 |  |  | 83.93% | 595876.36 | 80% on-going
Completion of Covered Court-Panamoren |  |  |  |  | Laak | 1565000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Covered Court-Sabud |  |  |  |  | Laak | 1665000 |  |  | 0.8836% | 14712.76 | Completed on Sept 28, 2018
Completion of Covered Court-Ampawid |  |  |  |  | Laak | 1870000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Covered Court-Sto.Niño |  |  |  |  | Laak | 1020000 |  |  | 0.9731% | 9925.31 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Sisimon |  |  |  |  | Laak | 985000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Covered Court-Imelda |  |  |  |  | Laak | 1405000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Covered Court-Datu Ampunan |  |  |  |  | Laak | 2260000 |  |  | 0.4425% | 10000 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Bollucan |  |  |  |  | Laak | 1490000 |  |  | 0.8239% | 12275.95 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Amor Cruz |  |  |  |  | Laak | 1890000 |  |  | 0.9318% | 17611.63 | Contract Bidded last Sept 12, 2018
PROGRAM OR PROJECT |  |  |  |  | LOCATION |  | DATE STARTED |  | OBLIGATION
[6 empty] | TOTAL COST |  | TARGET | % OF | TOTAL | REMARKS
[6 empty] | Appropriation |  | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[8 empty] | DATE | APPROPRIATION | TO DATE
Completion of Covered Court-Mangloy |  |  |  |  | Laak | 910000 |  |  | 0.7061% | 6425.96 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-El Papa |  |  |  |  | Laak | 1000000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Covered Court-Longganapan |  |  |  |  | Laak | 645000 |  |  | 0.8925% | 5756.92 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Langtud |  |  |  |  | Laak | 755000 |  |  | 1.105% | 8344.02 | Contract Bidded last Sept 12, 2018
Completion of Covered Court-Mabuhay |  |  |  |  | Laak | 810000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Covered Court-Kapatagan |  |  |  |  | Laak | 795000 |  |  | 0% |  | Declared Savings for SB#2
Completion of Multi-Purpose Hall-New Leyte |  |  |  |  | Maco | 1000000 |  |  | 0% |  | Fund Transfer to Municipality (FTM)
Completion of Health Center-Mapaang |  |  |  |  | Maco | 1500000 |  |  | 0% |  | For change in Nomenclature
Improvement of Multi-Purpose Building |  |  |  |  | Maragusan | 5000000 |  |  | 0% |  | Fund Transfer to Municipality (FTM)
Completion of Covered Court-Kinuban |  |  |  |  | Maco | 1000000 |  |  | 3% | 30000 | Contract Bidded last Sept 12, 2018
Concreting of Road from Purok 2, to Poblacion-DENR Administration Bldg. |  |  |  |  | Nabunturan | 1500000 |  |  | 65.18% | 977663.28 | 50% on-going
Construction of PDEA Multi-Purpose Building, PPO |  |  |  |  | Nabunturan | 1000000 |  |  | 72.44% | 724449.16 | 15% on-going
Concreting of CVPH Montevista road networks |  |  |  |  | Montevista | 1000000 |  |  | 91.86% | 918647.98 | Completed on Sept 28, 2018
Concreting of CVPH Pantukan road networks |  |  |  |  | Pantukan | 1000000 |  |  | 85.67% | 856671.06 | 70% on-going
1918 (C.O)
Repair/Rehabilitation of Water System | [5 empty] | 5000000 |  |  | 99.85% | 4992456 | On-going
Concreting of Road from Prk 4 to crossing going to prk 1 Baybay Brgy Tambongon |  |  |  |  | Pantukan | 2000000 |  |  | 0% |  | Purchase Order on process
Concreting/Upgrading of Road @ Kalantas St. Brgy. Pob to Prk Aguinaldo |  |  |  |  | Brgy. Langgam, Maco | 1000000 |  |  | 6.494% | 64936 | R.I.S on process
Concreting of Road leading to Brgy. Hall Brgy. Andap |  |  |  |  | New Bataan | 1500000 |  |  | 0% |  | For abandonment. Actual road too steep etc.
Improvement of Covered Court Brgy. Fatima |  |  |  |  | New Bataan | 700000 |  |  | 0% |  | Contract. Notice of Award issued on Sept 18, 2018
Constion of Footbridge, Log Cabin, Prk 3 Brgy Bukal |  |  |  |  | Nabunturan | 2500000 |  |  | 0% |  | Contract Purchase Request on process
Purchase of Lot for the Construction of MP Hall |  |  |  |  | Brgy Bongabong, Pantukan | 700000 |  |  | 100% | 700000 | Transfer of Funds
Construction of Gymnasium |  |  |  |  | Brgy. Kidawa, Laak | 2500000 |  |  | 0% |  | Contract. Notice of Award issued on Sept 18, 2018
Improvement of Gymnasium |  |  |  |  | Brgy. Kahayag New Bataan | 700000 |  |  | 0% |  | Contract. Notice of Award issued on Sept 18, 2018
Construction of Tribal Hall |  |  |  |  | Brgy. Elizalde, Maco | 500000 |  |  | 0% |  | Program of work approved. PPMP on process
Construction of Tribal Hall |  |  |  |  | New Bataan | 500000 |  |  | 0% |  | Contract. Notice of Award issued on Sept 18, 2018
PROGRAM OR PROJECT |  |  |  |  | LOCATION |  | DATE STARTED |  | OBLIGATION
[6 empty] | TOTAL COST |  | TARGET | % OF | TOTAL | REMARKS
[6 empty] | Appropriation |  | COMPLETION | OBLIGATION/ | COST INCURRED | (Project Status)
[8 empty] | DATE | APPROPRIATION | TO DATE
Construction of Tribal Hall |  |  |  |  | Maragusan | 500000 |  |  | 0% |  | Contract. Purchase Request on process
Construction of Covered Court, Brgy. Andap, Laak |  |  |  |  | Laak | 147933.82 |  |  | 87.32% | 129172.96 | Completed on Sept 28, 2018
Construction of Brgy. Stage Brgy. Magnaga |  |  |  |  | Pantukan | 231546.6 |  |  | 79.64% | 184404.38 | Completed on June 29, 2018
Construction of Covered Court Brgy. Banbanon, Laak |  |  |  |  | Laak | 149098.67 |  |  | 68.61% | 102293.75 | Completed on July 31, 2018
Construction of Covered Court Brgy. Bagong Silang |  |  |  |  | Laak | 249273.02 |  |  | 52.26% | 130273.29 | Completed on June 29, 2018
Construction of Covered Court Brgy. Kiokmay |  |  |  |  | Laak | 221137.31 |  |  | 64.3% | 142185.27 | Completed on July 31, 2018
Construction of Covered Court Brgy. New Bethlehem |  |  |  |  | Laak | 98784.86 |  |  | 57.45% | 56749.5 | Completed on July 31, 2018
Construction of Covered Court Brgy. Cabuyuan, Mabini |  |  |  |  | Mabini | 118685.62 |  |  | 88.67% | 105235.35 | Completed on May 31, 2018
Concreting of Road from Prk 3 to Prk 6 Brgy. Mainit |  |  |  |  | Nabunturan | 8355000 |  |  |  |  | Contract. Purchase Request on process
Electrification of Sitio Kilabot, Brgy. Ngan, Compostela |  |  |  |  | Compostela | 700000 |  |  |  |  | Contract. Purchase Request on process
Sub - Total | [5 empty] | 116094459.9 |  |  |  | 13111010.65
[7 empty] | DATE STARTED |  | PROJECT STATUS
[8 empty] | TARGET |  | TOTAL
[8 empty] | COMPLETION | % OF | COST INCURRED
PROGRAM OR PROJECT |  |  |  |  | LOCATION | TOTAL COST |  | DATE | COMPLETION | TO DATE
8917 (MOOE)
ECONOMIC DEVELOPMENT:
| Maintenance of roads/bridges - District 1 |  |  |  | Provincewide | 28917741 | 2018-01-02 | 2018-12-31 | 75.26% | 21763441.49 | On-going.
| Maintenance of roads/bridges - District 2 |  |  |  | Provincewide | 28584229 | 2018-01-02 | 2018-12-31 | 77.9% | 22265790.58 | On-going.
| Repair/Rehabilitation of Farm-to-Market Roads (FMR) |  |  |  |  | 5000000 |  |  | 94.53% | 4726642.21 | On-going.
Sub - Total | [5 empty] | 62501970 |  |  |  | 48755874.28
9911 (MOOE)
Loan Amortization - Domestic
Financial Expenses
|  | Interest Expenses |  |  |  | 23673930 |  |  | 54.5% | 12901151.54 | Paid to Land Bank of the Philippines
|  | Loans Payable |  |  |  | 88795653 |  |  | 70.46% | 62564883.24 | Paid to Land Bank of the Philippines
Sub - Total | [5 empty] | 112469583 |  |  |  | 75466034.78
Grand Total | [5 empty] | 291066012.9 |  |  |  | 137332919.71
Summary: | [8 empty] | %of Obligation/
[6 empty] | Appropriation |  |  | Appropriation | Obligation
| 1918 | Social Development |  |  |  | 116094459.9
|  | Declared Savings SB#2 |  |  |  | -9055000
[6 empty] | 107039459.9 |  |  | 12.25% | 13111010.65
| 8917 | Economic Development |  |  |  | 62501970 |  |  | 78% | 48755874.28
| 9911 | Financial Expenses |  |  |  | 112469583 |  |  | 67% | 75466034.78
|  | Total |  |  |  | 282011012.9
Republic of the Philippines
PROVINCE OF COMPOSTELA VALLEY
Capitol Building, Cabidianan, Nabunturan, Compostela Valley
20% COMPONENT OF THE IRA UTILIZATION
As of September 30, 2018
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained
in this document.
|  |  | As to Appropriation/Obligation |  |  | As to Project Status: |  |  |  | Approved:
|  |  | (SGD.) Eva Jean S. Licayan, Enp,REB,MPA |  | (SGD.) omeo B. Celeste,EnP |  | (SGD.)Engr. Roderick M. Digamon |  |  | (SGD.) Jayvee Tyron L. Uy, MPA
|  |  | Provincial Budget Officer |  | Provincial Planning & Development Office |  | Provincial Engineer's Office |  |  | Governor

## Sheet1
40000000
1080000
905000
1000000
500000
750000
500000
1300000
1300000
1300000
1300000
500000
370000
875000
880000
625000
705000
58000
1000000
710000
1565000
1665000
1870000
1020000
985000
1405000
2260000
1490000
1890000
910000
1000000
645000
755000
810000
795000
1000000
1500000
5000000
1000000
1500000
1000000
1000000
1000000
5000000
2000000
1000000
1500000
700000
2500000
700000
2500000
700000
500000
500000
500000
147933.82
231546.6
149098.67
249273.02
221137.31
98784.86
118685.62
8355000
700000
116094459.9